## SWA(02-20-26)
Q
As of February 27, 2026
Project Title: | REPAIR OF VICENTE TRINIDAD NATIONAL HIGH SCHOOL GYMNASIUM, IGUIG, CAGAYAN
Location: | Iguig, Cagayan
ITEM | DESCRIPTION OF WORK |  | UNIT | UNIT | PROGRAMMED | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/ | [6 empty] | 802 | Excavation
NO. |  |  |  | PRICE | QUANTITY | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS | #REF! | [5 empty] | Length | Width | Height | Qty | Volume | Unit
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | each | 12431.85 | 1 | 12431.85 | 0.5188% |  | 12431.85 | 12431.85 | 0.5188% | COMPLETED | 100% | 1 |  |  |  |  | 804(b) | Gravel Bedding
B.7 | Construction Safety and Health Program |  | l.s | 40072.39 | 1 | 40072.39 | 1.672% |  | 40072.39 | 40072.39 | 1.672% | COMPLETED | 100% | 1 |  |  |  |  | Length | Width | Thickness | Qty | Volume | Unit
B.9 | Mobilization/ Demobilization |  | l.s | 17850 | 1 | 17850 | 0.7449% |  | 17850 | 17850 | 0.7449% | COMPLETED | 100% | 1 |  |  |  |  | 1.5 | 1.5 | 0.1 |  | 0 | #REF!
II | WORK ITEMS
801(3)a | Removal of Actual Structures and Obstructions |  | sq.m | 5866.86 | 9.6 | 56321.856 | 2.35% |  | 56321.856 | 56321.856 | 2.35% | COMPLETED | 100% | 9.6 |  |  |  |  | 900 (a) | Reinforced Concrete Column Footing
405(1) | Structural Concrete |  | cu.m | 20566.58 | 2.4 | 49359.792 | 2.06% |  | 49359.792 | 49359.792 | 2.06% | COMPLETED | 100% | 2.4
1032 | Painting works |  | sq.m | 484.1 | 165.6 | 80166.96 | 3.346% |  | 80166.96 | 80166.96 | 3.346% | COMPLETED | 100% | 165.6
1047 | Metal Structure |  | kg | 111.35 | 13421.88 | 1494526.338 | 62.37% |  | 1494526.338 | 1494526.338 | 62.37% | COMPLETED | 100% | 13421.88
1014 | Pre-Painted Metal Sheets |  | sq.m | 952.6 | 574.56 | 547325.856 | 22.84% |  | 547325.856 | 547325.856 | 22.84% | COMPLETED | 100% | 574.56
1103 | Electrical Works |  | units | 8179.78 | 12 | 98157.36 | 4.096% |  | 98157.36 | 98157.36 | 4.096% | COMPLETED | 100% | 12
T O T A L S | [5 empty] | 2396212.402 | 100% |  | 2396212.402 | 2396212.402 | 100% | COMPLETED
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 100%
[5 empty] | TOTAL PROJECT COST |  |  | 2396212.402
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 2396212.402
[5 empty] | LESS ADVANCED PAYMENT |  |  | 359431.8603
[5 empty] | TOTAL THIS VOUCHER |  |  | 2036780.5417
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
DIXIE R. CABRERA |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.)
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
Q
As of _____________________, 2020
A. | CONCRETING OF FARM TO MARKET ROAD ZIMINILA
CAMALANIUGAN, CAGAYAN
ITEM | DESCRIPTION OF WORK |  |  | PROGRAMMED | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  |  | QUANTITY | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
|  |  |  | ORIGINAL | [12 empty] | 16%
105(1) | Sub Grade Preparation |  |  | 1075.8 | 102.17 | 109364.91 | 10.0228 |  |  | 0 | #REF! | on-going |  |  |  | 109914.486 | 17586.3178 | 92328.1682
200(1) | Aggregate Sub Base Coarse |  |  | 173.25 | 804.58 | 223636.89 | 20.4954 |  |  | 0 | 0% | on-going |  |  |  | 139393.485 | 22302.9576 | 117090.5274
311(1)C | PCCP |  |  | 660 | 72.96 | 672973.03 | 61.6752 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 48153.6 | 7704.576 | 40449.024
B.9 | Mobilization/ Demobilization |  |  | 1 | 128.93 | 25951.88 | 2.3784 |  |  | 0 | 0% | on-going |  | 604.87 | #REF! | 128.93 | 20.6288 | 108.3012
B.5 | Billboards and Signages |  |  | 2 | 18.37 | 10196.76 | 0.93449 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 36.74 | 5.8784 | 30.8616
B.7 | Occupational Health and Safety |  |  | 1 | 1208.89 | 28041.09 | 2.5698 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 1208.89 | 193.4224 | 1015.4676
A.1.1(8a) | Provisions of Field Office for the Engineer |  |  | 1.83 | 1291.19 | 20992.58 | 1.9239 |  |  | 0 | 0% | on-going |  | 1067.5 |  | 2362.8777 | 378.0604 | 1984.8173
T O T A L S | [5 empty] | 1091157.14 | 100 | 0 | 0 | 0 | #REF! |  |  |  |  | 301199.0087 | 48191.8414 | 253007.1673
[14 empty] | #REF! |  | 1957.7936
299241.2151
[5 empty] | % THIS ACCOMPLISHMENT |  |  | #REF! |  | %
[5 empty] | TOTAL PROJECT COST |  |  | 1091157.14
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 0
MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 0
Requested by: |  | Prepared by: |  |  | Checked by: |  |  |  | Approved:
EV INTERIOR CONSTRUCTION |  | MARISSA A. MACADANGDANG |  |  | MA. VICTORIA E. REYES |  |  |  | MANUEL N. MAMBA, M.D.
Contractor |  | Engineering Assistant |  |  | Engineer II |  |  |  | Governor