## SWA (July 6-9)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-08
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[15 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 0 | 0 | 0% | Not Yet Started | 0 | 0.415%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 7780.5 | 7780.5 | 0.26% | On going | 0.5 | 0.261%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 14744.1 | 14744.1 | 0.494% | On going | 0.5 | 0.493%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 25754.4288 | 25754.4288 | 0.862% | On going | 44.225 | 0.862%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 0 |  | 0% | Not Yet Started | 0 | 0.921%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 11841.8558 | 11841.8558 | 0.396% | On going | 83.025 | 0.397%
III. | SUB-BASE COURSE
200(1) | Aggregates Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 0 |  | 0% | Not Yet Started | 0 | 1.346%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 0 |  | 0% | Not Yet Started
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 0 |  | 0% | Not Yet Started
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 0 |  | 0% | Not Yet Started | 0 | 5.988%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  |  | 0% | Not Yet Started
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 0 | 0 | 0% | Not Yet Started | 0 | 14.15%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 0 |  | 0% | Not Yet Started
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 0 |  | 0% | Not Yet Started
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 0 |  | 0% | Not Yet Started
T O T A L S | [5 empty] | 2987425.2642 | 100% |  | 76897.747 | 76897.747 | 2.574% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 2.574%
[5 empty] | TOTAL PROJECT COST |  |  | 2987425.2642
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 76897.747
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 76897.747
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
24.83%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  | 49.66%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0

## STEWA (July 6-9)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-07-08 |  |  |  | To be Filled In | 2026-07-08 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-07-08
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [6 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 7
11. | Percentage of work accomplished - Actual | : | 2.574% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 1.334% |  | Don't Fill In | 1.334% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 1.24% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 7.368% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
As of
CAGANDA 2025

## SWA (July 13-17)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-17
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[15 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 0 | 0 | 0% | Not Yet Started | 0 | 0.415%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 7780.5 | 7780.5 | 0.26% | On going | 0.5 | 0.261%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 14744.1 | 14744.1 | 0.494% | On going | 0.5 | 0.493%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 51508.8575 | 51508.8575 | 1.724% | COMPLETED | 88.45 | 0%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 0 |  | 0% | Not Yet Started | 0 | 0.921%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 11841.8558 | 11841.8558 | 0.396% | On going | 83.025 | 0.397%
III. | SUB-BASE COURSE
200(1) | Aggregates Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 0 |  | 0% | Not Yet Started | 0 | 1.346%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 0 |  | 0% | Not Yet Started
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 0 |  | 0% | Not Yet Started
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 0 |  | 0% | Not Yet Started | 0 | 5.988%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  |  | 0% | Not Yet Started
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 0 | 0 | 0% | Not Yet Started | 0 | 14.15%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 386311.7638 | 386311.7638 | 12.93% | On going
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 305159.4622 | 305159.4622 | 10.21% | On going
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 501808.0589 | 501808.0589 | 16.8% | On going
T O T A L S | [5 empty] | 2987425.2642 | 100% |  | 1295931.4605 | 1295931.4605 | 43.38% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 43.38%
[5 empty] | TOTAL PROJECT COST |  |  | 2987425.2642
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 1295931.4605
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 1295931.4605
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
23.97%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  | 47.93%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0

## STEWA (July 13-17)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-07-17 |  |  |  | To be Filled In | 2026-07-17 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-07-17
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [6 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 16
11. | Percentage of work accomplished - Actual | : | 43.38% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 6.837% |  | Don't Fill In | 6.837% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 36.54% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 16.84% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
As of
CAGANDA 2025

## SWA (July 20-24)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-17
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[15 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 0 | 0 | 0% | Not Yet Started | 0 | 0.415%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 7780.5 | 7780.5 | 0.26% | On going | 0.5 | 0.261%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 14744.1 | 14744.1 | 0.494% | On going | 0.5 | 0.493%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 51508.8575 | 51508.8575 | 1.724% | COMPLETED | 88.45 | 0%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 0 |  | 0% | Not Yet Started | 0 | 0.921%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 11841.8558 | 11841.8558 | 0.396% | On going | 83.025 | 0.397%
III. | SUB-BASE COURSE
200(1) | Aggregates Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 0 |  | 0% | Not Yet Started | 0 | 1.346%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 0 |  | 0% | Not Yet Started
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 0 |  | 0% | Not Yet Started
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 0 |  | 0% | Not Yet Started | 0 | 5.988%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  |  | 0% | Not Yet Started
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 0 | 0 | 0% | Not Yet Started | 0 | 14.15%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 482889.7047 | 482889.7047 | 16.16% | COMPLETED
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 381449.3277 | 381449.3277 | 12.77% | COMPLETED
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 627260.0736 | 627260.0736 | 21% | COMPLETED
T O T A L S | [5 empty] | 2987425.2642 | 100% |  | 1594251.2818 | 1594251.2818 | 53.36% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 53.36%
[5 empty] | TOTAL PROJECT COST |  |  | 2987425.2642
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 1594251.2818
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 1594251.2818
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
23.97%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  | 47.93%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0

## STEWA (July 20-24)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-07-24 |  |  |  | To be Filled In | 2026-07-24 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-07-24
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [6 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 23
11. | Percentage of work accomplished - Actual | : | 43.38% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 13.78% |  | Don't Fill In | 13.78% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 29.6% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 24.21% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
As of
CAGANDA 2025

## SWA (July 27-30)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-17
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[15 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 0 | 0 | 0% | Not Yet Started | 0 | 0.415%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 7780.5 | 7780.5 | 0.26% | On going | 0.5 | 0.261%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 14744.1 | 14744.1 | 0.494% | On going | 0.5 | 0.493%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 51508.8575 | 51508.8575 | 1.724% | COMPLETED | 88.45 | 0%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 27527.998 | 27527.998 | 0.921% | COMPLETED | 40.85 | 0%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 11841.8558 | 11841.8558 | 0.396% | On going | 83.025 | 0.397%
III. | SUB-BASE COURSE
200(1) | Aggregates Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 0 |  | 0% | Not Yet Started | 0 | 1.346%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 0 |  | 0% | Not Yet Started
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 0 |  | 0% | Not Yet Started
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 89440.7415 | 89440.7415 | 2.994% | On going | 749.65 | 2.994%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  | 106617.6276 | 3.569% | On going
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 211296.431 | 211296.431 | 7.073% | On going | 35.645 | 7.073%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 482889.7047 | 482889.7047 | 16.16% | COMPLETED
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 381449.3277 | 381449.3277 | 12.77% | COMPLETED
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 627260.0736 | 627260.0736 | 21% | COMPLETED
T O T A L S | [5 empty] | 2987425.2642 | 100% |  | 1922516.4523 | 2029134.0798 | 67.92% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 67.92%
[5 empty] | TOTAL PROJECT COST |  |  | 2987425.2642
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 1922516.4523
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 1922516.4523
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
12.98%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  | 25.96%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0

## STEWA (July 27-30)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-07-30 |  |  |  | To be Filled In | 2026-07-30 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-07-30
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [6 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 29
11. | Percentage of work accomplished - Actual | : | 67.92% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 21.28% |  | Don't Fill In | 21.28% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 46.64% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 30.53% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
[6 empty] | WRITE "L" - OPT TO USE LINEAR |  | ANDEAGEIL.CSU
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
As of
CAGANDA 2025

## SWA (August 3-7)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-17
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[15 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 12390 | 12390 | 0.415% | COMPLETED | 2 | 0%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 7780.5 | 7780.5 | 0.26% | On going | 0.5 | 0.261%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 14744.1 | 14744.1 | 0.494% | On going | 0.5 | 0.493%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 51508.8575 | 51508.8575 | 1.724% | COMPLETED | 88.45 | 0%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 27527.998 | 27527.998 | 0.921% | COMPLETED | 40.85 | 0%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 23683.7115 | 23683.7115 | 0.793% | COMPLETED | 166.05 | 0%
III. | SUB-BASE COURSE
200(1) | Aggregates Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 40202.6976 | 40202.6976 | 1.346% | COMPLETED | 42.64 | 0%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 0 |  | 0% | Not Yet Started
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 0 |  | 0% | Not Yet Started
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 178881.483 | 178881.483 | 5.988% | COMPLETED | 1499.3 | 0%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  | 213235.2552 | 7.138% | COMPLETED
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 422592.862 | 422592.862 | 14.15% | COMPLETED | 71.29 | 0%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 482889.7047 | 482889.7047 | 16.16% | COMPLETED
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 381449.3277 | 381449.3277 | 12.77% | COMPLETED
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 627260.0736 | 627260.0736 | 21% | COMPLETED
T O T A L S | [5 empty] | 2987425.2642 | 100% |  | 2287688.1781 | 2500923.4333 | 83.72% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 83.72%
[5 empty] | TOTAL PROJECT COST |  |  | 2987425.2642
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 2287688.1781
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 2287688.1781
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
0.754%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  | 1.508%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0

## STEWA (August 3-7)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-08-07 |  |  |  | To be Filled In | 2026-08-07 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-08-07
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [6 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 37
11. | Percentage of work accomplished - Actual | : | 83.72% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 32.99% |  | Don't Fill In | 32.99% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 50.73% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 38.95% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
[6 empty] | WRITE "L" - OPT TO USE LINEAR |  | ANDEAGEIL.CSU
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
As of
CAGANDA 2025

## SWA (August 10-14)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-17
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[15 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 12390 | 12390 | 0.415% | COMPLETED | 2 | 0%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 7780.5 | 7780.5 | 0.26% | On going | 0.5 | 0.261%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 14744.1 | 14744.1 | 0.494% | On going | 0.5 | 0.493%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 51508.8575 | 51508.8575 | 1.724% | COMPLETED | 88.45 | 0%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 27527.998 | 27527.998 | 0.921% | COMPLETED | 40.85 | 0%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 23683.7115 | 23683.7115 | 0.793% | COMPLETED | 166.05 | 0%
III. | SUB-BASE COURSE
200(1) | Aggregates Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 40202.6976 | 40202.6976 | 1.346% | COMPLETED | 42.64 | 0%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 0 |  | 0% | Not Yet Started
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 137026.5029 | 137026.5029 | 4.587% | COMPLETED
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 178881.483 | 178881.483 | 5.988% | COMPLETED | 1499.3 | 0%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  | 213235.2552 | 7.138% | COMPLETED
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 422592.862 | 422592.862 | 14.15% | COMPLETED | 71.29 | 0%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 482889.7047 | 482889.7047 | 16.16% | COMPLETED
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 381449.3277 | 381449.3277 | 12.77% | COMPLETED
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 627260.0736 | 627260.0736 | 21% | COMPLETED
T O T A L S | [5 empty] | 2987425.2642 | 100% |  | 2424714.681 | 2637949.9362 | 88.3% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 88.3%
[5 empty] | TOTAL PROJECT COST |  |  | 2987425.2642
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 2424714.681
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 2424714.681
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
0.754%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  | 1.508%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0

## STEWA (August 10-14)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-08-14 |  |  |  | To be Filled In | 2026-08-14 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-08-14
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [6 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 44
11. | Percentage of work accomplished - Actual | : | 88.3% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 44.23% |  | Don't Fill In | 44.23% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 44.08% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 46.32% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
[6 empty] | WRITE "L" - OPT TO USE LINEAR |  | ANDEAGEIL.CSU
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
As of
CAGANDA 2025

## SWA (August 17-21)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-17
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[15 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 12390 | 12390 | 0.415% | COMPLETED | 2 | 0%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 7780.5 | 7780.5 | 0.26% | On going | 0.5 | 0.261%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 14744.1 | 14744.1 | 0.494% | On going | 0.5 | 0.493%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 51508.8575 | 51508.8575 | 1.724% | COMPLETED | 88.45 | 0%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 27527.998 | 27527.998 | 0.921% | COMPLETED | 40.85 | 0%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 23683.7115 | 23683.7115 | 0.793% | COMPLETED | 166.05 | 0%
III. | SUB-BASE COURSE
200(1) | Aggregates Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 40202.6976 | 40202.6976 | 1.346% | COMPLETED | 42.64 | 0%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 163475.364 | 163475.364 | 5.472% | On going
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 137026.5029 | 137026.5029 | 4.587% | COMPLETED
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 178881.483 | 178881.483 | 5.988% | COMPLETED | 1499.3 | 0%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  | 213235.2552 | 7.138% | COMPLETED
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 422592.862 | 422592.862 | 14.15% | COMPLETED | 71.29 | 0%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 482889.7047 | 482889.7047 | 16.16% | COMPLETED
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 381449.3277 | 381449.3277 | 12.77% | COMPLETED
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 627260.0736 | 627260.0736 | 21% | COMPLETED
T O T A L S | [5 empty] | 2987425.2642 | 100% |  | 2588190.045 | 2801425.3002 | 93.77% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 93.77%
[5 empty] | TOTAL PROJECT COST |  |  | 2987425.2642
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 2588190.045
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 2588190.045
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
0.754%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  | 1.508%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0

## STEWA (August 17-21)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-08-21 |  |  |  | To be Filled In | 2026-08-21 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-08-21
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [6 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 51
11. | Percentage of work accomplished - Actual | : | 93.77% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 55.77% |  | Don't Fill In | 55.77% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 38% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 53.68% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
[6 empty] | WRITE "L" - OPT TO USE LINEAR |  | ANDEAGEIL.CSU
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
As of
CAGANDA 2025

## SWA (August 24-28)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-17
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[15 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 12390 | 12390 | 0.415% | COMPLETED | 2 | 0%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 7780.5 | 7780.5 | 0.26% | On going | 0.5 | 0.261%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 14744.1 | 14744.1 | 0.494% | On going | 0.5 | 0.493%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 51508.8575 | 51508.8575 | 1.724% | COMPLETED | 88.45 | 0%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 27527.998 | 27527.998 | 0.921% | COMPLETED | 40.85 | 0%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 23683.7115 | 23683.7115 | 0.793% | COMPLETED | 166.05 | 0%
III. | SUB-BASE COURSE
200(1) | Aggregates Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 40202.6976 | 40202.6976 | 1.346% | COMPLETED | 42.64 | 0%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 326950.728 | 326950.728 | 10.94% | COMPLETED
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 137026.5029 | 137026.5029 | 4.587% | COMPLETED
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 178881.483 | 178881.483 | 5.988% | COMPLETED | 1499.3 | 0%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  | 213235.2552 | 7.138% | COMPLETED
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 422592.862 | 422592.862 | 14.15% | COMPLETED | 71.29 | 0%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 482889.7047 | 482889.7047 | 16.16% | COMPLETED
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 381449.3277 | 381449.3277 | 12.77% | COMPLETED
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 627260.0736 | 627260.0736 | 21% | COMPLETED
T O T A L S | [5 empty] | 2987425.2642 | 100% |  | 2751665.409 | 2964900.6642 | 99.25% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 99.25%
[5 empty] | TOTAL PROJECT COST |  |  | 2987425.2642
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 2751665.409
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 2751665.409
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
0.754%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  | 1.508%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0
[16 empty] | 0 | 0

## STEWA (August 24-28)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-08-28 |  |  |  | To be Filled In | 2026-08-28 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-08-28
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [6 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 58
11. | Percentage of work accomplished - Actual | : | 99.25% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 67.01% |  | Don't Fill In | 67.01% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 32.23% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 61.05% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
[6 empty] | WRITE "L" - OPT TO USE LINEAR |  | ANDEAGEIL.CSU
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
As of
CAGANDA 2025

## SWA (FINAL)
STATEMENT OF WORK ACCOMPLISHMENT
|  |  |  | As of | 2026-07-08
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO
Location: | Cato, Tuao, Cagayan
[16 empty] | Feb 2-6, 2026 | Feb. 9-13, 2026 | Feb. 16-20, 2026 | Feb 23-27, 2026
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
ORIGINAL
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | Each | 6195 | 12390 | 0.415% |  | 12390 | 12390 | 0.415% | COMPLETED | 2 |  | 0%
B.7 | Construction Safety and Health Program |  | 1 | L.S. | 15561 | 15561 | 0.521% |  | 15561 | 15561 | 0.521% | COMPLETED | 1 |  | 0%
B.9 | Mobilization/ Demobilization |  | 1 | L.S. | 29488.2 | 29488.2 | 0.987% |  | 29488.2 | 29488.2 | 0.987% | COMPLETED | 1 |  | 0%
II. | WORK ITEMS
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) |  | 88.45 | sq.m | 582.35 | 51508.8575 | 1.724% |  | 51508.8575 | 51508.8575 | 1.724% | COMPLETED | 88.45 |  | 0%
101(6) | Removal of Structures and Obstruction |  | 40.85 | cu.m | 673.88 | 27527.998 | 0.921% |  | 27527.998 | 27527.998 | 0.921% | COMPLETED | 40.85 |  | 0%
103(1)a | Structure Excavation (Common Soil) |  | 36.25 | cu.m | 462.81 | 16776.8625 | 0.562% |  | 16776.8625 | 16776.8625 | 0.562% | COMPLETED | 36.25 |  | 0%
105(1) | Sub-Grade Preparation (Common Materials) |  | 166.05 | sq.m | 142.63 | 23683.7115 | 0.793% |  | 23683.7115 | 23683.7115 | 0.793% | COMPLETED | 166.05 |  | 0%
III. | SUB-BASE COURSE
200(1) | Aggregate Sub-Base Course |  | 42.64 | cu.m | 942.84 | 40202.6976 | 1.346% | 0 | 40202.6976 | 40202.6976 | 1.346% | COMPLETED | 42.64 |  | 0%
IV. | SURFACE COURSE
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) |  | 125.05 | sq.m | 2614.56 | 326950.728 | 10.94% |  | 326950.728 | 326950.728 | 10.94% | COMPLETED
311(2)e1 | Portland Cement Concrete Pavement (reinforced) |  | 49.07 | sq.m | 2792.47 | 137026.5029 | 4.587% |  | 137026.5029 | 137026.5029 | 4.587% | COMPLETED
V. | DRAINAGE AND SLOPE PROTECTION
a. | RETAINING WALL | [11 empty] | #DIV/0! |  | 0%
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) |  | 1499.3 | kgs | 119.31 | 178881.483 | 5.988% |  | 178881.483 | 178881.483 | 5.988% | COMPLETED | 1499.3 | 749.65 | 0%
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) |  | 1665.38 | kgs | 128.04 | 213235.2552 | 7.138% |  |  | 213235.2552 | 7.138% | COMPLETED |  | 832.69
405(1)a3 | Structural Concrete Class A (Retaining Wall) |  | 71.29 | cu.m | 5927.8 | 422592.862 | 14.15% |  | 422592.862 | 422592.862 | 14.15% | COMPLETED | 71.29 | 35.645 | 0%
b. | REINFORCED CONCRETE BOX CULVERT | [11 empty] | #DIV/0! |  | 0%
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) |  | 4406.33 | kgs | 109.59 | 482889.7047 | 16.16% |  | 482889.7047 | 482889.7047 | 16.16% | COMPLETED
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) |  | 3045.99 | kgs | 125.23 | 381449.3277 | 12.77% |  | 381449.3277 | 381449.3277 | 12.77% | COMPLETED
404(1)c | Structural Concrete Class A (RCBC Double Barrel) |  | 101.82 | cu.m | 6160.48 | 627260.0736 | 21% |  | 627260.0736 | 627260.0736 | 21% | COMPLETED
T O T A L S | [5 empty] | 2987425.2642 | #DIV/0! |  | 2774190.009 | 2987425.2642 | 100% |  | BOQ
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 100%
|  | 8.07 |  |  | TOTAL PROJECT COST |  |  | 2987425.2642
|  | 174.12 |  |  | TOTAL THIS ACCOMPLISHMENT |  |  | 2774190.009
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 2774190.009
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
0%
0%
PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | GEN. EDGAR B. AGLIPAY (RET.) |  |  |  |  | 0%
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
16%
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0
[17 empty] | 0 | 0

## STEWA (FINAL)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [8 empty] | single | WITHOUT REVISION
[9 empty] | in a relationship | WITH REVISION
| 2026-08-31 |  |  |  | To be Filled In | 2026-08-31 |  |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[9 empty] | married | ON THE EXPIRY DATE WITH REVISION
[9 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO |  | To be Filled In | CONSTRUCTION OF BOX CULVERT ALONG CATO-CONNER ROAD, TUAO | Project Name |  | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Cato, Tuao, Cagayan |  | To be Filled In | Cato, Tuao, Cagayan | Location |  | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3000000 |  | To be Filled In | 3000000 | Contract Amount |  | LDR_2 | WITH REVISION
Contractor |  | : | Dragonace Construction Corporation |  | To be Filled In | Dragonace Construction Corporation | Contractor
1. | Period Covered: | : | 2026-01-04 | to
2026-08-31
2. | Contract Duration | : | 95 |  | To be Filled In | 95 | Contract Duration |  | 2025-01-02 |  | 2026-01-08
3. | Date of Receipt of Notice to Proceed | : | 2025-12-26 |  | To be Filled In | 2025-12-26 | Date of Receipt of Notice to Proceed |  | -367 |  | 2026-07-06
4. | Expiry Date | : | 2026-04-09 | [7 empty] | 179
5. | Approved Time Extension | : |  |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 179 |  | To be Filled In | 179 | Approved Time Suspension
7. | Total Time Extension |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | 0 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-10-05 |  |  | 179
10. | Total Calendar days Elapsed to Date | : | 61
11. | Percentage of work accomplished - Actual | : | 100% |  |  |  | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 71.59% |  | Don't Fill In | 71.59% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | 28.41% |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ONGOING
[5 empty] | Don't Fill In | 64.21% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| PORFIRIO S. CANAPI |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
EMAIL: peo@cagayan.gov.ph
9
[8 empty] | 2026-04-29 | 75
2026-07-22
As of
CAGANDA 2025

## IAR RCBC JuLY 1-3)
Contract No.
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO - CONNER ROAD, TUAO
| Tuao, Cagayan |  |  |  |  | Municipality: |  | Tuao,Cagayan
Contractor: | DRAGONACE CONSTRUCTION CORPORATION |  |  |  |  | Week Covered: |  | JULY 1-3, 2026
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit |  |  |  | 4
[7 empty] | Physical | Billable
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) | [5 empty] | 44.225 |  | sq.m | 12.05
101(6) | Removal of Structures and Obstruction | [7 empty] | cu.m |  |  | 2.44
103(1)a | Structure Excavation (Common Soil) | [5 empty] | 36.25 |  | cu.m
105(1) | Sub-Grade Preparation (Common Materials) | [7 empty] | sq.m |  |  |  | 14.88
200(1) | Aggregates Sub-Base Course | [7 empty] | cu.m |  | 9.92 |  | 0.98
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) | [7 empty] | sq.m
311(2)e1 | Portland Cement Concrete Pavement (reinforced) | [7 empty] | sq.m
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) | [7 empty] | kgs
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) | [7 empty] | kgs
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [7 empty] | cu.m
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)c | Structural Concrete Class A (RCBC Double Barrel) | [7 empty] | sq.m
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
-REMOVAL OF ACTUAL STRUCTURES AND OBSTRUCTION
-INSTALLATION OF REBARS FOR BOX CULVERT
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
[5 empty] | Foreman |  | 1 | Transit Mixer | 1
[5 empty] | Leadman |  | 2 | Concrete Vibrator | 1
[5 empty] | Laborer |  | 8 | Back hoe | 1
[5 empty] | Operator |  | 2 | Jackhammer | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
| 1.24% |  | 2.574% |  | 1.334% |  | ON GOING
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
RENNIEL T. ARMAS |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## IAR RCBC JuLY 6-17)
Contract No.
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO - CONNER ROAD, TUAO
| Tuao, Cagayan |  |  |  |  | Municipality: |  | Tuao,Cagayan
Contractor: | DRAGONACE CONSTRUCTION CORPORATION |  |  |  |  | Week Covered: |  | JULY 6-17, 2026
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit |  |  |  | 4
[7 empty] | Physical | Billable
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) | [7 empty] | sq.m | 12.05
101(6) | Removal of Structures and Obstruction | [7 empty] | cu.m |  |  | 2.44
103(1)a | Structure Excavation (Common Soil) | [7 empty] | cu.m
105(1) | Sub-Grade Preparation (Common Materials) | [7 empty] | sq.m |  |  |  | 14.88
200(1) | Aggregates Sub-Base Course | [7 empty] | cu.m |  | 9.92 |  | 0.98
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) | [7 empty] | sq.m
311(2)e1 | Portland Cement Concrete Pavement (reinforced) | [7 empty] | sq.m
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) | [7 empty] | kgs
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) | [7 empty] | kgs
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [7 empty] | cu.m
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) | [5 empty] | 4406.33 |  | sq.m
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) | [5 empty] | 3045.99 |  | sq.m
404(1)c | Structural Concrete Class A (RCBC Double Barrel) | [5 empty] | 101.82 |  | sq.m
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
-INSTALLATION OF RSB FOR BOX CULVERT
-CONCRETE POURING OF BOX CULVERT
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
[5 empty] | Foreman |  | 1 | Transit Mixer | 1
[5 empty] | Leadman |  | 2 | Concrete Vibrator | 1
[5 empty] | Laborer |  | 8 | Back hoe
[5 empty] | Operator |  | 2 | Jackhammer
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
| 6.837% |  | 43.38% |  | 36.54% |  | ON GOING
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
RENNIEL T. ARMAS |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## IAR RCBC JuLY 20-24)
Contract No.
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO - CONNER ROAD, TUAO
| Tuao, Cagayan |  |  |  |  | Municipality: |  | Tuao,Cagayan
Contractor: | DRAGONACE CONSTRUCTION CORPORATION |  |  |  |  | Week Covered: |  | JULY 20-24, 2026
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit |  |  |  |  | 4
[7 empty] | Physical | Billable
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) | [7 empty] | sq.m | 12.05
101(6) | Removal of Structures and Obstruction | [7 empty] | cu.m |  |  |  | 2.44
103(1)a | Structure Excavation (Common Soil) | [7 empty] | cu.m
105(1) | Sub-Grade Preparation (Common Materials) | [7 empty] | sq.m |  |  |  |  | 14.88
200(1) | Aggregates Sub-Base Course | [7 empty] | cu.m |  | 9.92 |  |  | 0.98
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) | [7 empty] | sq.m
311(2)e1 | Portland Cement Concrete Pavement (reinforced) | [7 empty] | sq.m
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) | [7 empty] | kgs |  |  | 749.65
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) | [7 empty] | kgs |  |  | 832.69
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [7 empty] | cu.m |  |  | 35.645
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) | [5 empty] | 881.266 |  | sq.m
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) | [5 empty] | 609.198 |  | sq.m
404(1)c | Structural Concrete Class A (RCBC Double Barrel) | [5 empty] | 20.364 |  | sq.m
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
-INSTALLATION OF RSB FOR BOX CULVERT
-CONCRETE POURING OF BOX CULVERT
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
[5 empty] | Foreman |  | 1 | Transit Mixer | 1
[5 empty] | Leadman |  | 2 | Concrete Vibrator | 1
[5 empty] | Laborer |  | 8 | Back hoe
[5 empty] | Operator |  | 2 | Jackhammer
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
| 13.78% |  | 53.36% |  | 39.59% |  | ON GOING
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
RENNIEL T. ARMAS |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## IAR RCBC JuLY 27-30)
Contract No.
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO - CONNER ROAD, TUAO
| Tuao, Cagayan |  |  |  |  | Municipality: |  | Tuao,Cagayan
Contractor: | DRAGONACE CONSTRUCTION CORPORATION |  |  |  |  | Week Covered: |  | JULY 27-30, 2026
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit |  |  |  | 4
[7 empty] | Physical | Billable
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) | [7 empty] | sq.m | 12.05
101(6) | Removal of Structures and Obstruction | [7 empty] | cu.m |  |  | 2.44
103(1)a | Structure Excavation (Common Soil) | [7 empty] | cu.m
105(1) | Sub-Grade Preparation (Common Materials) | [7 empty] | sq.m |  |  |  | 14.88
200(1) | Aggregates Sub-Base Course | [7 empty] | cu.m |  | 9.92 |  | 0.98
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) | [7 empty] | sq.m
311(2)e1 | Portland Cement Concrete Pavement (reinforced) | [7 empty] | sq.m
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) | [5 empty] | 749.65 |  | kgs
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) | [5 empty] | 832.69 |  | kgs
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [5 empty] | 35.645 |  | cu.m
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)c | Structural Concrete Class A (RCBC Double Barrel) | [7 empty] | sq.m
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
-INSTALLATION OF RSB FOR RETAINING WALL
-CONCRETE POURING OF RETAINING WALL
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
[5 empty] | Foreman |  | 1 | Transit Mixer | 1
[5 empty] | Leadman |  | 2 | Concrete Vibrator | 1
[5 empty] | Laborer |  | 8 | Back hoe
[5 empty] | Operator |  | 2 | Jackhammer
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
| 21.28% |  | 67.92% |  | 46.64% |  | ON GOING
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
RENNIEL T. ARMAS |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## IAR RCBC Aug 3-7)
Contract No.
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO - CONNER ROAD, TUAO
| Tuao, Cagayan |  |  |  |  | Municipality: |  | Tuao,Cagayan
Contractor: | DRAGONACE CONSTRUCTION CORPORATION |  |  |  |  | Week Covered: |  | AUGUST 3-7, 2026
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit |  |  |  | 4
[7 empty] | Physical | Billable
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) | [7 empty] | sq.m | 12.05
101(6) | Removal of Structures and Obstruction | [7 empty] | cu.m |  |  | 2.44
103(1)a | Structure Excavation (Common Soil) | [7 empty] | cu.m
105(1) | Sub-Grade Preparation (Common Materials) | [7 empty] | sq.m |  |  |  | 14.88
200(1) | Aggregates Sub-Base Course | [5 empty] | 42.64 |  | cu.m |  | 9.92 |  | 0.98
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) | [7 empty] | sq.m
311(2)e1 | Portland Cement Concrete Pavement (reinforced) | [7 empty] | sq.m
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) | [5 empty] | 749.65 |  | kgs
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) | [5 empty] | 832.69 |  | kgs
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [5 empty] | 35.645 |  | cu.m
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)c | Structural Concrete Class A (RCBC Double Barrel) | [7 empty] | sq.m
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
-INSTALLATION OF RSB FOR RETAINING WALL
-CONCRETE POURING OF RETAINING WALL
-BACKFILLING AND PREPARATION (SUBBASE COURSE)
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
[5 empty] | Foreman |  | 1 | Transit Mixer | 1
[5 empty] | Leadman |  | 2 | Concrete Vibrator | 1
[5 empty] | Laborer |  | 8 | Back hoe
[5 empty] | Operator |  | 2 | Roller | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
| 32.99% |  | 83.72% |  | 50.73% |  | ON GOING
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
RENNIEL T. ARMAS |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## IAR RCBC Aug 10-14)
Contract No.
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO - CONNER ROAD, TUAO
| Tuao, Cagayan |  |  |  |  | Municipality: |  | Tuao,Cagayan
Contractor: | DRAGONACE CONSTRUCTION CORPORATION |  |  |  |  | Week Covered: |  | AUGUST 10-14, 2026
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit |  |  |  | 4
[7 empty] | Physical | Billable
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) | [7 empty] | sq.m | 12.05
101(6) | Removal of Structures and Obstruction | [7 empty] | cu.m |  |  | 2.44
103(1)a | Structure Excavation (Common Soil) | [7 empty] | cu.m
105(1) | Sub-Grade Preparation (Common Materials) | [7 empty] | sq.m |  |  |  | 14.88
200(1) | Aggregates Sub-Base Course | [7 empty] | cu.m |  | 9.92 |  | 0.98
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) | [7 empty] | sq.m
311(2)e1 | Portland Cement Concrete Pavement (reinforced) | [5 empty] | 49.07 |  | sq.m
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) | [7 empty] | kgs
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) | [7 empty] | kgs
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [7 empty] | cu.m
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)c | Structural Concrete Class A (RCBC Double Barrel) | [7 empty] | sq.m
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
-INSTALLATION OF RSB FOR REINFORCED PCCP
-CONCRETE POURING OF PCCP
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
[5 empty] | Foreman |  | 1 | Transit Mixer | 1
[5 empty] | Leadman |  | 2 | Concrete Vibrator | 1
[5 empty] | Laborer |  | 8 | Back hoe
[5 empty] | Operator |  | 2 | Roller | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
| 44.23% |  | 88.3% |  | 44.08% |  | ON GOING
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
RENNIEL T. ARMAS |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## IAR RCBC Aug 17-21)
Contract No.
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO - CONNER ROAD, TUAO
| Tuao, Cagayan |  |  |  |  | Municipality: |  | Tuao,Cagayan
Contractor: | DRAGONACE CONSTRUCTION CORPORATION |  |  |  |  | Week Covered: |  | AUGUST 17-21, 2026
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit |  |  |  | 4
[7 empty] | Physical | Billable
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) | [7 empty] | sq.m | 12.05
101(6) | Removal of Structures and Obstruction | [7 empty] | cu.m |  |  | 2.44
103(1)a | Structure Excavation (Common Soil) | [7 empty] | cu.m
105(1) | Sub-Grade Preparation (Common Materials) | [7 empty] | sq.m |  |  |  | 14.88
200(1) | Aggregates Sub-Base Course | [7 empty] | cu.m |  | 9.92 |  | 0.98
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) | [5 empty] | 125.05 |  | sq.m
311(2)e1 | Portland Cement Concrete Pavement (reinforced) | [7 empty] | sq.m
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) | [7 empty] | kgs
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) | [7 empty] | kgs
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [7 empty] | cu.m
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)c | Structural Concrete Class A (RCBC Double Barrel) | [7 empty] | sq.m
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
-CONCRETE POURING OF UNREINFORCED PCCP
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
[5 empty] | Foreman |  | 1 | Transit Mixer | 1
[5 empty] | Leadman |  | 2 | Concrete Vibrator | 1
[5 empty] | Laborer |  | 8 | Back hoe
[5 empty] | Operator |  | 2 | Roller | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
| 55.77% |  | 100% |  | 44.23% |  | ON GOING
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
RENNIEL T. ARMAS |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## IAR RCBC Aug 24-31)
Contract No.
Project Title: | CONSTRUCTION OF BOX CULVERT ALONG CATO - CONNER ROAD, TUAO
| Tuao, Cagayan |  |  |  |  | Municipality: |  | Tuao,Cagayan
Contractor: | DRAGONACE CONSTRUCTION CORPORATION |  |  |  |  | Week Covered: |  | AUGUST 24-31, 2026
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit |  |  |  | 4
[7 empty] | Physical | Billable
101(3)b1 | Removal of Actual Structures/Obstructions (ACP) | [7 empty] | sq.m | 12.05
101(6) | Removal of Structures and Obstruction | [7 empty] | cu.m |  |  | 2.44
103(1)a | Structure Excavation (Common Soil) | [7 empty] | cu.m
105(1) | Sub-Grade Preparation (Common Materials) | [7 empty] | sq.m |  |  |  | 14.88
200(1) | Aggregates Sub-Base Course | [7 empty] | cu.m |  | 9.92 |  | 0.98
311(1)c | Portland Cement Concrete Pavement , 230mm thick (Unreinforced) | [5 empty] | 125.05 |  | sq.m
311(2)e1 | Portland Cement Concrete Pavement (reinforced) | [7 empty] | sq.m
404(1)a | Reiinforced Steel, Grade 40 (Retaining Wall) | [7 empty] | kgs
404(1)b | Reiinforced Steel, Grade 60 (Retaining Wall) | [7 empty] | kgs
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [7 empty] | cu.m
404(1)a | Reinforced Steel, Grade 40 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)b | Reinforced Steel, Grade 60 (RCBC Double Barrel) | [7 empty] | sq.m
404(1)c | Structural Concrete Class A (RCBC Double Barrel) | [7 empty] | sq.m
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
-CONCRETE POURING OF UNREINFORCED PCCP
-DEMOBALIZATION
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
[5 empty] | Foreman |  | 1 | Transit Mixer | 1
[5 empty] | Leadman |  | 2 | Concrete Vibrator | 1
[5 empty] | Laborer |  | 8 | Back hoe
[5 empty] | Operator |  | 2 | Roller | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
| 71.59% |  | 100% |  | 28.41% |  | ON GOING
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
RENNIEL T. ARMAS |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE