## 2-5-8-2024 (hidden)
Contract No. | B011 - 2023
Project Title: | Improvement of Road Network
| A. Padul Solana - Tuao Road Solana, Cagayan | [5 empty] | Municipality: |  | Tuao
| B. Bugnay Tuao to Solana Road Tuao, Cagayan | [5 empty] | Week Covered: |  | February 5-8, 2024
Contractor: | Dragonace Construction Corporation
ACCOMPLISHMENT
Item No. | Description |  |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[8 empty] | Physical | Billable
105(1) | Sub-Grade Preparation(Common Materials) |  |  |  | PCCP |  |  | 292.5 |  | sq.m.
200(1) | Aggregate Subbase Course |  |  |  | PCCP |  |  | 473.85 |  | cu.m.
311(1)c | Portland Cement Concrete Pavement, 230mm |  |  |  | PCCP |  |  | 292.5 |  | sq.m. | 72
[11 empty] | 97.5 | 68
3
292.5
FOR VARIATION ORDER
Item No. | Description |  |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: | [5 empty] | FIELD INSTRUCTIONS:
Preparation of Sub-grade
Pouring of Concrete for PCCP
Installation of forms for PCCP
Removal of forms for PCCP
PROBLEMS ENCOUNTERED/ REMARKS: | [5 empty] | MANPOWER |  |  | EQUIPMENT
[6 empty] | Description |  | Quantity | Description | Quantity
[6 empty] | Site Engineer |  | 1 | Transit Mixer | 2
[6 empty] | Foreman |  | 1 | Concrete Vibrator | 2
[6 empty] | Skilled Laborer |  | 4 | Screeder | 1
[6 empty] | Laborer |  | 8 | Loader | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET |  | ACTUAL |  | VARIANCE |  | REMARKS
| 84.35% |  |  | 70.55% |  | -13.8% |  | On-going
Prepared by: |  |  | Checked and Reviewed By: |  |  |  |  | Conforme:
ALLAN C. BELLO |  |  | PORFIRIO S. CANAPI |  |  |  |  | FERLYN BEA LARON
PEO Engineer I |  |  | PEO Engineer II |  |  |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 2-12-16-2024 (hidden)
Contract No. | B011 - 2023
Project Title: | Improvement of Road Network
| A. Padul Solana - Tuao Road Solana, Cagayan | [5 empty] | Municipality: |  | Tuao
| B. Bugnay Tuao to Solana Road Tuao, Cagayan | [5 empty] | Week Covered: |  | February 12-16, 2024
Contractor: | Dragonace Construction Corporation
ACCOMPLISHMENT
Item No. | Description |  |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[8 empty] | Physical | Billable
105(1) | Sub-Grade Preparation(Common Materials) |  |  |  | PCCP |  |  | 306 |  | sq.m.
200(1) | Aggregate Subbase Course |  |  |  | PCCP |  |  | 495.72 |  | cu.m.
311(1)c | Portland Cement Concrete Pavement, 230mm |  |  |  | PCCP |  |  | 306 |  | sq.m. | 72
[11 empty] | 102 | 68
3
306
FOR VARIATION ORDER
Item No. | Description |  |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: | [5 empty] | FIELD INSTRUCTIONS:
Preparation of Sub-grade
Pouring of Concrete for PCCP
Installation of forms for PCCP
Removal of forms for PCCP
PROBLEMS ENCOUNTERED/ REMARKS: | [5 empty] | MANPOWER |  |  | EQUIPMENT
[6 empty] | Description |  | Quantity | Description | Quantity
[6 empty] | Site Engineer |  | 1 | Transit Mixer | 2
[6 empty] | Foreman |  | 1 | Concrete Vibrator | 2
[6 empty] | Skilled Laborer |  | 4 | Screeder | 1
[6 empty] | Laborer |  | 8 | Loader | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET |  | ACTUAL |  | VARIANCE |  | REMARKS
| 85.62% |  |  | 71.89% |  | -13.73% |  | On-going
Prepared by: |  |  | Checked and Reviewed By: |  |  |  |  | Conforme:
GESIECA D. DUYAO |  |  | PORFIRIO S. CANAPI |  |  |  |  | FERLYN BEA LARON |  |  | 211.4%
PEO Engineer I |  |  | PEO Engineer II |  |  |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 2-19-23-2024 (hidden)
Contract No. | B011 - 2023
Project Title: | Improvement of Road Network
| A. Padul Solana - Tuao Road Solana, Cagayan | [5 empty] | Municipality: |  | Tuao
| B. Bugnay Tuao to Solana Road Tuao, Cagayan | [5 empty] | Week Covered: |  | February 19-23 2024
Contractor: | Dragonace Construction Corporation
ACCOMPLISHMENT
Item No. | Description |  |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[8 empty] | Physical | Billable
105(1) | Sub-Grade Preparation(Common Materials) |  |  |  | PCCP |  |  | 345 |  | sq.m.
200(1) | Aggregate Subbase Course |  |  |  | PCCP |  |  | 558.9 |  | cu.m.
311(1)c | Portland Cement Concrete Pavement, 230mm |  |  |  | PCCP |  |  | 345 |  | sq.m. | 72
[11 empty] | 115 | 68
3
345
FOR VARIATION ORDER
Item No. | Description |  |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: | [5 empty] | FIELD INSTRUCTIONS:
Preparation of Sub-grade
Pouring of Concrete for PCCP
Installation of forms for PCCP
Removal of forms for PCCP
PROBLEMS ENCOUNTERED/ REMARKS: | [5 empty] | MANPOWER |  |  | EQUIPMENT
[6 empty] | Description |  | Quantity | Description | Quantity
[6 empty] | Site Engineer |  | 1 | Transit Mixer | 2
[6 empty] | Foreman |  | 1 | Concrete Vibrator | 2
[6 empty] | Skilled Laborer |  | 8 | Screeder | 1
[6 empty] | Laborer |  | 16 | Loader | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET |  | ACTUAL |  | VARIANCE |  | REMARKS
| 86.96% |  |  | 72.93% |  | -14.03% |  | On-going
Prepared by: |  |  | Checked and Reviewed By: |  |  |  |  | Conforme:
GESIECA D. DUYAO |  |  | PORFIRIO S. CANAPI |  |  |  |  | FERLYN BEA LARON |  |  | 211.4%
PEO Engineer I |  |  | PEO Engineer II |  |  |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 2-26--3-1-2024 (hidden)
Contract No. | B011 - 2023
Project Title: | Improvement of Road Network
| A. Padul Solana - Tuao Road Solana, Cagayan | [5 empty] | Municipality: |  | Tuao
| B. Bugnay Tuao to Solana Road Tuao, Cagayan | [5 empty] | Week Covered: |  | February 26 - March 1, 2024
Contractor: | Dragonace Construction Corporation
ACCOMPLISHMENT
Item No. | Description |  |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[8 empty] | Physical | Billable
105(1) | Sub-Grade Preparation(Common Materials) |  |  |  | PCCP |  |  | 270 |  | sq.m.
200(1) | Aggregate Subbase Course |  |  |  | PCCP |  |  | 437.4 |  | cu.m.
311(1)c | Portland Cement Concrete Pavement, 230mm |  |  |  | PCCP |  |  | 270 |  | sq.m. | 72
[11 empty] | 90 | 68
3
270
FOR VARIATION ORDER
Item No. | Description |  |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: | [5 empty] | FIELD INSTRUCTIONS:
Preparation of Sub-grade
Pouring of Concrete for PCCP
Installation of forms for PCCP
Removal of forms for PCCP
PROBLEMS ENCOUNTERED/ REMARKS: | [5 empty] | MANPOWER |  |  | EQUIPMENT
[6 empty] | Description |  | Quantity | Description | Quantity
[6 empty] | Site Engineer |  | 1 | Transit Mixer | 2
[6 empty] | Foreman |  | 1 | Concrete Vibrator | 2
[6 empty] | Skilled Laborer |  | 4 | Screeder | 1
[6 empty] | Laborer |  | 8 | Loader | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET |  | ACTUAL |  | VARIANCE |  | REMARKS
| 88.99% |  |  | 73.58% |  | -15.41% |  | On-going
Prepared by: |  |  | Checked and Reviewed By: |  |  |  |  | Conforme:
GESIECA D. DUYAO |  |  | PORFIRIO S. CANAPI |  |  |  |  | FERLYN BEA LARON |  |  | 211.4%
PEO Engineer I |  |  | PEO Engineer II |  |  |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 3-4-8-2024 (hidden)
Contract No. | B011 - 2023
Project Title: | Improvement of Road Network
| A. Padul Solana - Tuao Road Solana, Cagayan | [5 empty] | Municipality: |  | Tuao
| B. Bugnay Tuao to Solana Road Tuao, Cagayan | [5 empty] | Week Covered: |  | March 4 - 8, 2024
Contractor: | Dragonace Construction Corporation
ACCOMPLISHMENT
Item No. | Description |  |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[8 empty] | Physical | Billable
105(1) | Sub-Grade Preparation(Common Materials) |  |  |  | PCCP |  |  | 337.5 |  | sq.m.
200(1) | Aggregate Subbase Course |  |  |  | PCCP |  |  | 546.75 |  | cu.m.
311(1)c | Portland Cement Concrete Pavement, 230mm |  |  |  | PCCP |  |  | 337.5 |  | sq.m. | 72
[11 empty] | 112.5 | 68
3
337.5
FOR VARIATION ORDER
Item No. | Description |  |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: | [5 empty] | FIELD INSTRUCTIONS:
Preparation of Sub-grade
Pouring of Concrete for PCCP
Installation of forms for PCCP
Removal of forms for PCCP
PROBLEMS ENCOUNTERED/ REMARKS: | [5 empty] | MANPOWER |  |  | EQUIPMENT
[6 empty] | Description |  | Quantity | Description | Quantity
[6 empty] | Site Engineer |  | 1 | Transit Mixer | 2
[6 empty] | Foreman |  | 1 | Concrete Vibrator | 2
[6 empty] | Skilled Laborer |  | 8 | Screeder | 1
[6 empty] | Laborer |  | 12 | Loader | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET |  | ACTUAL |  | VARIANCE |  | REMARKS
| 91.01% |  |  | 74.32% |  | -16.69% |  | On-going
Prepared by: |  |  | Checked and Reviewed By: |  |  |  |  | Conforme:
GESIECA D. DUYAO |  |  | PORFIRIO S. CANAPI |  |  |  |  | FERLYN BEA LARON |  |  | 211.4%
PEO Engineer I |  |  | PEO Engineer II |  |  |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 3-18-22-2024 (hidden)
Contract No. | B011 - 2023
Project Title: | Improvement of Road Network
| A. Padul Solana - Tuao Road Solana, Cagayan | [5 empty] | Municipality: |  | Tuao
| B. Bugnay Tuao to Solana Road Tuao, Cagayan | [5 empty] | Week Covered: |  | March 25-27, 2024
Contractor: | Dragonace Construction Corporation
ACCOMPLISHMENT
Item No. | Description |  |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[8 empty] | Physical | Billable
105(1) | Sub-Grade Preparation(Common Materials) |  |  |  | PCCP |  |  | 225 |  | sq.m.
200(1) | Aggregate Subbase Course |  |  |  | PCCP |  |  | 364.5 |  | cu.m.
311(1)c | Portland Cement Concrete Pavement, 230mm |  |  |  | PCCP |  |  | 225 |  | sq.m. | 72
[11 empty] | 75 | 68
3
225
FOR VARIATION ORDER
Item No. | Description |  |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: | [5 empty] | FIELD INSTRUCTIONS:
Preparation of Sub-grade
Pouring of Concrete for PCCP
Installation of forms for PCCP
Removal of forms for PCCP
PROBLEMS ENCOUNTERED/ REMARKS: | [5 empty] | MANPOWER |  |  | EQUIPMENT
[6 empty] | Description |  | Quantity | Description | Quantity
[6 empty] | Site Engineer |  | 1 | Transit Mixer | 2
[6 empty] | Foreman |  | 1 | Concrete Vibrator | 2
[6 empty] | Skilled Laborer |  | 8 | Screeder | 1
[6 empty] | Laborer |  | 12 | Loader | 1
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET |  | ACTUAL |  | VARIANCE |  | REMARKS
| 96.07% |  |  | 86.32% |  | -9.75% |  | On-going
Prepared by: |  |  | Checked and Reviewed By: |  |  |  |  | Conforme:
GESIECA D. DUYAO |  |  | PORFIRIO S. CANAPI |  |  |  |  | ROREL S. FERNANDEZ |  |  | 211.4%
PEO Engineer I |  |  | PEO Engineer II |  |  |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## swa (hidden)
STATEMENT OF WORK ACCOMPLISHED
2024-01-17
Project Name |  | : | IMPROVEMENT OF ROAD NETWORK
A. PADUL SOLANA TO TUAO ROAD SOLANA, CAGAYAN
B. BUGNAY TUAO TO SOLANA ROAD TUAO, CAGAYAN
Project ID |  | : | B011-2023 | [11 empty] | accom | accom(inspection)
Location |  | : | SOLANA-TUAO, CAGAYAN | [11 empty] | 6/14/2023 | 2023-05-12
ITEM | DESCRIPTION OF WORK |  |  | PROGRAMMED |  | UNIT | AMOUNT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS
NO. |  |  |  | QUANTITY |  | COST |  | % | PREVIOUS | THIS PERIOD | TO DATE | %
A. | PADUL SOLANA TO TUAO ROAD SOLANA, CAGAYAN
PART A | FACILITIES FOR THE ENGINEERS
A.1.1 (8) | Provision of Field Office for the Engineer (Rental Basis) |  |  | month | 6 | 6195 | 37170 | 0.07087 | 27233.904 | 3717 | 30950.904 | 0.059012 | On-going |  | 5 | 4.3961 |  |  |  | 55680.66
PART B | OTHER GENERAL REQUIREMENTS | [18 empty] | 2526.58
B.5 | Billboards and Signages |  |  | each | 2 | 9912 | 19824 | 0.037797 | 19824 |  | 19824 | 0.037797 | On-going |  | 2 | 2 |  |  |  | 649545.75
B.7 | Construction Safety and Health Program |  |  | l.s. | all | 8053.5 | 8053.5 | 0.015355 | 5900.6792 | 805.35 | 6706.0292 | 0.012786 | On-going |  | 0.3 | 0.73269 |  |  |  | 620057.55
B.9 | Mobilization/Demobilization |  |  | l.s. | all | 204435 | 204435 | 0.38978 | 102217.5 |  | 102217.5 | 0.19489 | On-going |  | 0.5 | 0.5 |  |  |  | 7610185.8
PART C | EARTHWORKS | [18 empty] | 36532287.32
102(2) | Roadway Excavation (Surplus Common Excavation- Suitable Materials) |  |  | cu.m. | 1057.98 | 246.85 | 261162.363 | 0.49794 | 221988.0085 |  | 221988.0085 | 0.42325 | On-going |  | 555 | 899.283 |  |  |  | 45173.94
104(1) | Embankment |  |  | cu.m. | 5971.01 | 332.88 | 1987629.8088 | 3.7897 | 1689485.3375 |  | 1689485.3375 | 3.2212 | On-going |  | 1500 | 5075.3585 |  |  |  | 49961.44
105(1) | Sub-Grade Preparation(Common Materials) |  |  | sq.m. | 20444.4 | 18.64 | 381083.616 | 0.72659 | 0 |  | 0 | 0 | Not Yet Started |  | 5467.5 |  |  |  |  | 50224.1
PART D | SUBBASE COURSE | [5 empty] | 0 |  | 0 | [5 empty] | 0
200(1) | Aggregate Subbase Course |  |  | cu.m. | 6057.6 | 584.03 | 3537820.128 | 6.7453 | 0 |  | 0 | 0 | Not Yet Started |  | 1093.5 |  |  |  |  | 45615643.14
PART E | SURFACE COURSE | [5 empty] | 0 |  | 0 | [5 empty] | 0
311(1)C | Portland Cement Concrete Pavement, 230mm |  |  | sq.m. | 15396.4 | 1204.01 | 18537419.564 | 35.3441 | 0 |  | 0 | 0 | Not Yet Started | 24974597.9798 | 2058.75 |  |  | 0.73269 |  | 50224.1
S U B - T O T A L ( A ) | [8 empty] | 2066649.4292 | 4522.35 | 2071171.7792 | 3.949
B. | BUGNAY TUAO TO SOLANA ROAD TUAO, CAGAYAN
PART A | FACILITIES FOR THE ENGINEERS | [13 empty] | 0 |  |  |  |  | 91225829.72
A.1.1 (8) | Provision of Field Office for the Engineer (Rental Basis) |  |  | month | 5.5 | 6195 | 34072.5 | 0.064964 | 24964.412 | 10221.75 | 35186.162 | 0.067087 | On-going |  |  | 4.0298 |  | 11.5 |  | 50224.1
PART B | OTHER GENERAL REQUIREMENTS | [16 empty] | 345
B.5 | Billboards and Signages |  |  | each | 2 | 9912 | 19824 | 0.037797 | 19824 |  | 19824 | 0.037797 | On-going |  |  | 2
B.7 | Construction Safety and Health Program |  |  | l.s. | all | 23541 | 23541 | 0.044884 | 17248.1392 |  | 17248.1392 | 0.032886 | On-going |  |  | 0.73269
B.9 | Mobilization/Demobilization |  |  | l.s. | all | 251517 | 251517 | 0.47955 | 125758.5 |  | 125758.5 | 0.23978 | On-going |  |  | 0.5
PART C | EARTHWORKS
101(4)a1 | Removal of Actual Structures/Obstruction (610mmø RCPC) |  |  | ln.m. | 30 | 556.52 | 16695.6 | 0.031832 | 5565.2 |  | 5565.2 | 0.010611 | On-going |  |  | 10
101(4)a3 | Removal of Actual Structures/Obstruction (910mmø RCPC) |  |  | ln.m. | 16 | 521.74 | 8347.84 | 0.015916 | 8347.84 |  | 8347.84 | 0.015916 | On-going |  |  | 16
102(2) | Roadway Excavation (Surplus Common Excavation- Suitable Materials) |  |  | cu.m. | 2269.29 | 245.87 | 557950.3323 | 1.0638 | 474257.7825 |  | 474257.7825 | 0.90424 | On-going |  |  | 1928.8965
103(1)a | Structure Excavation |  |  | cu.m. | 354.11 | 116.49 | 41250.2739 | 0.078649 | 24602.688 |  | 24602.688 | 0.046908 | On-going |  |  | 235 | 211.2
103(6) | Pipe Culvert and Drain Excavation |  |  | cu.m. | 18.25 | 469.72 | 8572.39 | 0.016344 | 13527.936 |  | 13527.936 | 0.025793 | On-going |  |  | 28.8 |  |  |  | 181229753.66
104(1) | Embankment |  |  | cu.m. | 5528.47 | 274.96 | 1520108.1112 | 2.8983 | 1292091.8945 |  | 1292091.8945 | 2.4635 | On-going |  |  | 4699.1995 |  |  |  | 50224.1
105(1) | Sub-Grade Preparation(Common Materials) |  |  | sq.m. | 19367.1 | 18.73 | 362745.783 | 0.69162 | 501092.8677 | 16407.48 | 517500.3477 | 0.98668 | On-going | 651 | 225 | 26753.49
PART D | SUBBASE COURSE | [5 empty] | 0 |  | 0 | 0 | [9 empty] | 318322084.36
200(1) | Aggregate Subbase Course |  |  | cu.m. | 5738.4 | 584.61 | 3354726.024 | 6.3962 | 1249461.8148 | 829631.7432 | 2079093.558 | 3.9641 | On-going | 1054.62 | 364.5 | 2137.257
PART E | SURFACE COURSE | [5 empty] | 0 |  | 0 | 0
311(1)c | Portland Cement Concrete Pavement, 230mm |  |  | sq.m. | 14585.1 | 1201.82 | 17528664.882 | 33.4207 | 12842991.0387 | 1187999.07 | 14030990.1087 | 26.752 | On-going | 651 | 337.5 | 10686.285
PART F | DRAINAGE AND SLOPE PROTECTION STRUCTURES | [5 empty] | 0 |  | 0
| a. Line Drainage | [5 empty] | 0 |  | 0
404(1) | Reinforcing Steel |  |  | kgs. | 3771.94 | 73.56 | 277463.9064 | 0.52902 | 0 |  | 0 | 0 | Not Yet Started
405(1) | Structural Concrete Class A |  |  | cu.m. | 57.46 | 6120.11 | 351661.5206 | 0.67049 | 0 |  | 0 | 0 | Not Yet Started
| b. Retaining Wall | [5 empty] | 0 |  | 0
404(1) | Reinforcing Steel |  |  | kgs. | 13075.1 | 79.83 | 1043785.233 | 1.9901 | 949366.4266 |  | 949366.4266 | 1.8101 | On-going |  |  | 18273.6012 | 11892.3516
405(1) | Structural Concrete Class A |  |  | cu.m. | 241.88 | 6788.65 | 1642038.662 | 3.1308 | 1493503 |  | 1493503 | 2.8476 | On-going |  |  | 270.9255 | 220 |  | 54.0561
| 1.) 5 Units - 610mmø RCPC (Single) | [5 empty] | 0 |  | 0
404(1) | Reinforcing Steel |  |  | kgs. | 874.7 | 84.94 | 74297.018 | 0.14166 | 74297.018 |  | 74297.018 | 0.14166 | Completed |  |  | 874.7
405(1) | Structural Concrete Class A |  |  | cu.m. | 12.5 | 6822.72 | 85284 | 0.16261 | 85284 |  | 85284 | 0.16261 | Completed |  |  | 12.5
500(1)a1 | Reinforced Concrete Pipe Culvert, 610mmø |  |  | ln.m. | 9 | 3657.25 | 32915.25 | 0.062757 | 32915.25 |  | 32915.25 | 0.062757 | Completed |  |  | 9
| 2.) 1 Unit - 910mmø RCPC (Single0 | [5 empty] | 0 |  | 0
404(1) | Reinforcing Steel |  |  | kgs. | 272.06 | 94.02 | 25579.0812 | 0.04877 | 25579.0812 |  | 25579.0812 | 0.04877 | Completed |  | 36.86 | 272.06
405(1) | Structural Concrete Class A |  |  | cu.m. | 4.3 | 7016.27 | 30169.961 | 0.057523 | 30169.961 |  | 30169.961 | 0.057523 | Completed |  | 40.7515 | 4.3
500(1)a3 | Reinforced Concrete Pipe Culvert, 910mmø |  |  | ln.m. | 9 | 4272.97 | 38456.73 | 0.073323 | 38456.73 |  | 38456.73 | 0.073323 | Completed |  | 3.8915 | 9
| 3.) 1 Unit - 910mmø RCPC (Double) | [5 empty] | 0 |  | 0
404(1) | Reinforcing Steel |  |  | kgs. | 365.18 | 87.94 | 32113.9292 | 0.061229 | 0 |  | 0 | 0 | Not Yet Started
405(1) | Structural Concrete Class A |  |  | cu.m. | 6.24 | 6570.9 | 41002.416 | 0.078177 | 0 |  | 0 | 0 | Not Yet Started
500(1)a3 | Reinforced Concrete Pipe Culvert, 910mmø |  |  | ln.m. | 18 | 3949.62 | 71093.16 | 0.13555 | 0 |  | 0 | 0 | Not Yet Started | 27473876.6038
S U B - T O T A L ( B ) | [8 empty] | 19329305.5801 | 2044260.0432 | 21373565.6233 | 40.7515
T O T A L | [6 empty] | 52448474.5736 | 100 | 21395955.0094 | 2048782.3932 | 23444737.4026 | 44.7005
[5 empty] | % THIS ACCOMPLISHMENT |  |  |  | 44.7% |  |  |  |  | 52448474.57
[5 empty] | TOTAL PROJECT COST |  |  |  | 52448474.5736
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  |  | 23444737.4026 |  |  |  |  | -0.0036 | difference
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  |  | 23444737.4026
Prepared by: Checked by: | [6 empty] | Recommending Approval: |  |  |  | Approved:
PORFIRIO S. CANAPI ARNOLD L. MANUEL | [6 empty] | KINGSTON JAMES S. DELA CRUZ |  |  |  | MANUEL N. MAMBA
Engineer II OIC Chief - Construction Division | [6 empty] | Provincial Engineer |  |  |  | Governor
\
as of ________________________

## stewa (hidden)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
JUST FILL IN ON BLUE CELL!!!
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED
LEGEND:
| 2024-03-22 |  |  |  | * | To be Filled In | single | WITHOUT REVISION
[7 empty] | in a relationship | WITH REVISION
[7 empty] | complicated | ON THE EXPIRY DATE WITHOUT REVISION
Project Name |  | : | IMPROVEMENT OF ROAD NETWORK |  | * | To be Filled In | married | ON THE EXPIRY DATE WITH REVISION
|  | : | A. PADUL SOLANA TO TUAO ROAD SOLANA, CAGAYAN
|  | : | B. BUGNAY TUAO TO SOLANA ROAD TUAO, CAGAYAN
Location |  | : | SOLANA-TUAO, CAGAYAN |  | * | To be Filled In | separated | ON THE COMPLETION DATE WITHOUT REVISION
Contract Amount |  | : | 52448474.5736 |  | * | To be Filled In | divorced | ON THE COMPLETION DATE WITH REVISION
Contractor |  | : | DRAGONACE CONSTRUCTION CORPORATION / |  | * | To be Filled In | LDR_1 | WITHOUT REVISION
|  |  | MG JACINTO CONSTRUCTION JOINT VENTURE |  |  |  | LDR_2 | WITH REVISION
1. | Period Covered: | : | 2023-04-30 | to
2024-03-22
2. | Contract Duration | : | 345 |  |  |  | To be Filled In | 345 | Contract Duration
3. | Date of Receipt of Notice to Proceed | : | 2023-04-20 |  | * | To be Filled In
4. | Expiry Date | : | 2024-04-08
5. | Approved Time Extension | : | 0 |  |  |  | To be Filled In | 0 | Approved Time Extension
6. | Approved Time Suspension | : | 0 |  |  |  | To be Filled In |  | Approved Time Suspension
7. | Total Time Extension |  | 0 |  |  |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  |  |  | Don't Fill In | 0 | Revised Contract Duration |  | \
9. | Revised Expiry Date | :
10. | Total Calendar days Elapsed to Date | : | 328
11. | Percentage of work accomplished - Actual | : | 85.32%
12. | Percentage of work accomplished -Planned | : | 95.07% |  |  |  | Don't Fill In | 99.4% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | -9.752% |  |  |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | : | ON-GOING
[7 empty] | Don't Fill In | 95.07% | LINEAR - Planned (WITHOUT time extension)
[7 empty] | Don't Fill In |  | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted : |  |  |  | WRITE "F" - OPT TO USE FORMULA |  |  | l
WRITE "L" - OPT TO USE LINEAR
| PORFIRIO S. CANAPI |  | ARNOLD L. MANUEL
| Engineer II |  | OIC Chief - Construction Division
82.3
As of

## 3 - 25-27 - 2024 (hidden)
Contract No. | B011 - 2023
Project Title: | Improvement of Road Network
| A. Padul Solana - Tuao Road Solana, Cagayan |  |  |  |  | Municipality: |  | Tuao
Contractor: | B. Bugnay Tuao to Solana Road Tuao, Cagayan |  |  |  |  | Week Covered: |  | March 25-27, 2024
Dragonace Construction Corporation
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
72
[10 empty] | 112.5 | 68
3
337.5
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
________________________ |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL |  |  | ________________________ |  | #REF!
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 4 - 1-5 - 2024 (hidden)
Contract No.
Project Title: | Concreting of Barangay Road, Alcala, Cagayan –
| Malalatan Barangay Road, Alcala, Cagayan |  |  |  |  | Municipality: |  | Alcala
Contractor: | M.G. Jacinto Construction |  |  |  |  | Week Covered: |  | April 1 - 5, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
72
[10 empty] | 112.5 | 68
3
337.5
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
________________________ |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL |  |  | ________________________ |  | #REF!
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 4 - 8-12 - 2024 (hidden)
Contract No.
Project Title: | Concreting of Barangay Road, Alcala, Cagayan –
| Malalatan Barangay Road, Alcala, Cagayan |  |  |  |  | Municipality: |  | Alcala
Contractor: | M.G. Jacinto Construction |  |  |  |  | Week Covered: |  | April 8 - 12, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
72
[10 empty] | 112.5 | 68
3
337.5
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
________________________ |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL |  |  | ________________________ |  | #REF!
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 4 - 15-19 - 2024 (hidden)
Contract No.
Project Title: | Concreting of Barangay Road, Alcala, Cagayan –
| Malalatan Barangay Road, Alcala, Cagayan |  |  |  |  | Municipality: |  | Alcala
Contractor: | M.G. Jacinto Construction |  |  |  |  | Week Covered: |  | April 15 - 19, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
72
[10 empty] | 112.5 | 68
3
337.5
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
________________________ |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL |  |  | ________________________ |  | #REF!
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## 4 - 22-26 - 2024 (hidden)
Contract No.
Project Title: | Concreting of Barangay Road, Alcala, Cagayan –
| Malalatan Barangay Road, Alcala, Cagayan |  |  |  |  | Municipality: |  | Alcala
Contractor: | M.G. Jacinto Construction |  |  |  |  | Week Covered: |  | April 22 - 26, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
72
[10 empty] | 112.5 | 68
3
337.5
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conforme:
________________________ |  | PORFIRIO S. CANAPI |  |  | ARNOLD L. MANUEL |  |  | ________________________ |  | #REF!
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
85.62
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## CONCRETING (hidden)
Contract No.
Project Title: | CONSTRUCTION OF FARM TO MARKET ROAD IN THE PROVINCE OF CAGAYAN
| JOAQUIN DELA CRUZ FARM TO MARKET ROAD, CAMALANIUGAN |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | RARR CONSTRUCTION |  |  |  |  | Week Covered: |  | #REF!
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [7 empty] | each
B.7 | Construction Safety and Health Program | [7 empty] | l.s
B.9 | Mobilization/ Demobilization | [7 empty] | l.s
II | EARTHWORKS
102(2) | Surplus Common Excavation | [7 empty] | cu.m
104(1)a | Embankment from Roadway Excavation (Common Soil) | [7 empty] | cu.m
105(1)a | Sub-grade Preparation (Common Materials) | [7 empty] | sq.m.
III | SUB-BASE COURSE
200(1) | Aggregate Sub-base Course | [7 empty] | cu.m
IV | SUB-BASE COURSE
311(1)c1 | Portland Cement Concrete Pavement (Unreinforced), 230mm thk. | [7 empty] | sq.m.
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
GLORY VEE A. ARIBBAY |  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## Asassi
Contract No.
Project Title: | Infrastructure Development for Public Schools - Construction of Multipurpose Building - Gymnasium Asassi Integrated School
[6 empty] | Municipality: |  | BAGGAO, CAGAYAN
Contractor: | RJR'S Construction |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [7 empty] | Each
B.7 | Construction Safety & Health Program | [7 empty] | L.S.
B.9 | Mobilization/Demobilization | [7 empty] | L.S.
II | Work Items
802 | Excavation | [7 empty] | cu.m
804(a) | Backfilling | [7 empty] | cu.m
804(b) | Gravel Bedding | [7 empty] | cu.m
900 | Reinforced Concrete | [7 empty] | cu.m
902 | Reinforcing Steel Bars | [7 empty] | kg
903 | Formworks and Falseworks | [7 empty] | sq.m
1046 | Masonry Works | [7 empty] | sq.m
1027 | Cement Plaster finish | [7 empty] | sq.m
1032 | Painting Works | [7 empty] | sq.m
1047 | Metal structure | [7 empty] | kg
1014 | Pre-Painted Metal Sheets | [7 empty] | sq.m
1100 | Conduit, Boxes & Fittings | [7 empty] | lump sum
1101 | Wires and Wiring Devices | [7 empty] | lump sum
1102 | Power Load Center, Switchgear and panelboards, and Other Overcurrent Protection Devices | [7 empty] | lot
1103 | Lighting Fixtures and Lamps | [7 empty] | lot
1109 | Grounding System | [7 empty] | lot
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## PHO Phase II
Contract No.
Project Title: | Construction of Various Infrastructure Projects Upgrading/Improvement of
| Provincial Health office Phase II, Capitol Compound, Tuguegarao City |  |  |  |  | Municipality: |  | TUGUEGARAO CITY, CAGAYAN
Contractor: | Genten Builders |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [7 empty] | set
B.7 | Construction safety & Health Program | [7 empty] | l.s
B.9 | Mobilization/Demobilization | [7 empty] | lot
II | WORK ITEMS
803 | Structure Excavation | [7 empty] | cu.m
804(1) | Embankment | [7 empty] | cu.m
900(a) | Reinforced Concrete Works for Column Footing | [7 empty] | cu.m
900(b) | Reinforced Concrete Works for Column | [7 empty] | cu.m
900(c) | Reinforced Concrete Works for Slab | [7 empty] | cu.m
900(d) | Reinforced Concrete Works for Tie Beam | [7 empty] | cu.m
900(e) | Reinforced Concrete Works for Roof Beam | [7 empty] | cu.m
900(f) | Reinforced Concrete Works for Handhole & Encasement | [7 empty] | cu.m
903 | Formworks and Falseworks | [7 empty] | bd.ft
1046 | Masonry Works | [7 empty] | sq.m
1027(1) | Cement Plaster Finish | [7 empty] | sq.m
1014 | Pre-Painted Metal Sheets | [7 empty] | sq.m
1016 | Waterproofing | [7 empty] | sq.m
1032(1)a | Painting Works (Masonry and Concrete) | [7 empty] | sq.m
1032(1)b | Painting Works (Ficem Board) | [7 empty] | sq.m
1003(1)e1 | Ceiling Metal Frame Ficem Board | [7 empty] | sq.m
1007(1)b | Aluminum Framed Glass Door | [7 empty] | lot
1008 | Aluminum Glass Window | [7 empty] | sq.m
1018(1) | Ceramic Tiles | [7 empty] | sq.m
1100 | Conduit, Boxes & Fittings | [7 empty] | lot
1101 | Wires and Wiring Devices | [7 empty] | lot
1102 | Power Load Center, Switchgear and Panelboards, and Other | [7 empty] | lot
1103 | Lighting Fixtures and Lamps | [7 empty] | lot
1109 | Grounding System | [7 empty] | lot | a
1002 | Plumbing Works | [7 empty] | lot
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## Gas Station
Contract No.
Project Title: | Construction of Gas Station at Capitol Compound, Tuguegarao City
[6 empty] | Municipality: |  | TUGUEGARAO CITY, CAGAYAN
Contractor: | San Jacinto Construction Services |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [7 empty] | each
B.7 | Construction Safety & Health Program | [7 empty] | l.s
B.9 | Mobilization/Demobilization | [7 empty] | l.s
II | WORK ITEMS
606 b | Pavement markings | [7 empty] | sq.m
627 | Concrete bollard/protection post | [7 empty] | l.s
801a | Removal of Structures/Obstruction | [7 empty] | sq.m
801b | Removal of Structures/Obstruction | [7 empty] | each
801c | Relocation of Utilities | [7 empty] | l.s
803 | Structure Excavation | [7 empty] | cu.m
804(a) | Embankment | [7 empty] | cu.m
804(b) | Gravel Bed | [7 empty] | cu.m
900a | Reinforced Concrete (Foundation) | [7 empty] | cu.m
900b | Reinforced Concrete (Column) | [7 empty] | cu.m
900c | Reinforced Concrete (Grade Beam) | [7 empty] | cu.m
900d | Reinforced Concrete (Beam-01) | [7 empty] | cu.m
900e | Reinforced Concrete (Corbel) | [7 empty] | cu.m
900f | Reinforced Concrete (Pump Island Slab on Fill) | [7 empty] | cu.m
900g | Reinforced Concrete (Tank Pavement Slab on Fill) | [7 empty] | cu.m
900h | Reinforced Concrete (Cashier Booth Roof Slba) | [7 empty] | cu.m
900i | Reinforced Concrete (Wall Footing) | [7 empty] | cu.m
900j | Reinforced Concrete (MDP TRENCHWAY) | [7 empty] | cu.m
900k | Reinforced Concrete (Vent Riser Pipe Transition) | [7 empty] | cu.m
903 | Formworks and Falseworks | [7 empty] | sq.m
1001 | Storm Drainage and Seewerage System | [7 empty] | l.m
1003 | Carpentry and Joinery Works | [7 empty] | sq.m
1004 | Finishing Hardware | [7 empty] | sq.m
1005 | Louver Window | [7 empty] | sq.m
1007 | Aluminum Framed Glass Door | [7 empty] | l.s
1008 | Aluminum Glass Windows | [7 empty] | sq.m
1011(1)b | Roll-Up Doors | [7 empty] | l.s
1014 | Prepainted Metal Sheets | [7 empty] | sq.m
1016 | Waterproofing | [7 empty] | sq.m
1018 | Ceramic/Granite Tiles | [7 empty] | sq.m
1027 | Cement Plaster Finish | [7 empty] | sq.m
1032 | Painting, Varnishing & Other Related Works | [7 empty] | sq.m
1046 | Masonry Works | [7 empty] | sq.m
1047 | Metal Structure | [7 empty] | kgs.
1100 | Conduit, Boxes & Fittings | [7 empty] | l.s
1101 | Wires and Wiring Devices | [7 empty] | l.s
1102 | Power Load Center, Switchgear and Panelboards, and | [7 empty] | l.s
Other Overcurrent Protection Devices
1103 | Lighting Fixtures and Lamps | [7 empty] | l.s
1111 | Miscellaneous Electrical/Civil Works | [7 empty] | cu.m
1724 | Bulk Fuel Storage Tank | [7 empty] | set
1725 | Fuel Transfer Pump | [7 empty] | set
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## FMR Road
Contract No.
Project Title: | Improvement/Concreting of Roads - Concreting of the Portion of FMR Road
| at Barangay Baculud, Amulung, Cagayan |  |  |  |  | Municipality: |  | AMULUNG, CAGAYAN
Contractor: | MIG Aggregates and Concrete Products |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | FACILITIES FOR ENGINEERS
A.1.1 (11) | Provision of Furnitures/Fixtures, Equipment & Appliances for the Field Office for the Engineer | [7 empty] | L.S
II | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [7 empty] | Each
B.7 | Construction Safety & Health Program | [7 empty] | L.S
B.9 | Mobilization/Demobilization | [7 empty] | L.S
III | EARTHWORKS
101(4)a1 | Removal of Actual Structures/Obstruction (610mmØ RCPC) | [7 empty] | ln.m
101(4)a3 | Removal of Actual Structures/Obstruction (910mmØ RCPC) | [7 empty] | ln.m
102(2) | Roadway Excavation (Surplus Common Excavation) | [7 empty] | cu.m
103(1)a | Structure Excavation (Common Soil) | [7 empty] | cu.m
103(6)a | Pipe Culvert and Drain Excavation (Common Soil) | [7 empty] | cu.m
104(1)a | Embankment from Roadway Excavation | [7 empty] | cu.m
105(1) | Sub-Grade Preparation (Common Soil) | [7 empty] | sq.m
IV | SUB-BASE COURSE
200(1) | Aggregate Sub-Base Course | [7 empty] | cu.m
V | SURFACE COURSE
311(1)c1 | Portland Cement Concrete Pavemnet (Unreinforced) | [7 empty] | sq.m
230mm thk.
311(2)e1 | Portland Cement Concrete Pavemnet (Reinforced) | [7 empty] | sq.m
0.28m thk.
VI | DRAINAGE AND SLOPE PROTECTION
1 | Retaining Wall
404(1)a | Reinforcing Steel, Grade 40 (Retaining Wall) | [7 empty] | kgs.
404(1)b | Reinforcing Steel, Grade 60 (Retaining wall) | [7 empty] | kgs.
405(1)a3 | Structural Concrete Class A (Retaining Wall) | [7 empty] | cu.m
2 | Reinforced Concrete Box Culvert (Single Barrel)
404(1)a | Reinforcing Steel, Grade 40 (RCBC Single Barrel) | [7 empty] | kgs.
404(1)b | Reinforcing Steel, Grade 60 (RCBC Single Barrel) | [7 empty] | kgs.
405(1)a3 | Structural Concrete Class A (RCBC Single Barrel) | [7 empty] | cu.m
3 | Reinforced Concrete Pipe Culvert
404(1)a | Reinforcing Steel, Grade 40 (610mmØ RCPC) | [7 empty] | kgs
404(1)b | Reinforcing Steel, Grade 60 (610mmØ RCPC) | [7 empty] | kgs
405(1)a3 | Structural Concrete Class A (610mmØ RCPC) | [7 empty] | cu.m
500(1)a1 | Reinforced Concrete Pipe Culvert (610mmØ, Single) | [7 empty] | ln.m
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## Warehouse
Contract No.
Project Title: | Improvement of PEO Warehouse, Capitol Compound, Tuguegarao City
[7 empty] | Municipality: |  | TUGUEGARAO CITY, CAGAYAN
Contractor: | WBS Construction and Construction Supply | [5 empty] | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[8 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [8 empty] | Each
B.7 | Construction Safety & Health Program | [8 empty] | L.S
B.9 | Mobilization/Demobilization | [8 empty] | L.S
II | WORK ITEMS
801(3)a | Removal of Actual Structures/Obstruction | [8 empty] | lot
804(4) | Gravel Fill | [8 empty] | cu.m
900a | Reinforced Concrete (Slab on Grade) | [8 empty] | cu.m
900b | Reinforced Concrete (Septic Tank) | [8 empty] | cu.m
900c | Reinforced Concrete (Countertop Slab and Ledge) | [8 empty] | cu.m
903(1) | Formworks and Falseworks | [8 empty] | L.S
1046 | Masonry Works | [8 empty] | sq.m
1027(1) | Cement Plaster Finish | [8 empty] | sq.m
1018 | Ceramic Tile Works | [8 empty] | sq.m
1003(1) | Ceiling | . | [7 empty] | sq.m
1032 | Painting, Varnishing & Other Related Works | [8 empty] | sq.m
1002 | Plumbing Works | [8 empty] | lot
1010 | Doors | [8 empty] | sq.m
1008(1) | Aluminum Glass Windows | [8 empty] | sq.m
1100 | Conduit, Boxes & Fittings | [8 empty] | l.s
1101 | Wires and Wiring Devices | [8 empty] | l.s
1102(a) | Power Load Center, Switchgear and Panelboards, | [8 empty] | l.s
and other Overcurrent Protection Devices
1103 | Lighting Fixtures and Lamps | [8 empty] | l.s
Item No. | Description |  |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: | [5 empty] | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: | [5 empty] | MANPOWER |  |  | EQUIPMENT
[6 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET |  | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
rl
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD | [5 empty] | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION | [5 empty] | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[8 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: | [5 empty] | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: | [5 empty] | MANPOWER |  |  | EQUIPMENT
[6 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET |  | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  |  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## Kamaranan
Contract No.
Project Title: | Improvement of Provincial Government of Cagayan - Repair/Rehabilitation/
| Improvement of Kamaranan Building, Capitol Compounds, Tuguegarao City |  |  |  |  | Municipality: |  | TUGUEGARAO CITY, CAGAYAN
Contractor: | San Jacinto Construction Services |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard, Signages and Barricades | [7 empty] | each
B.7 | Construction Safety & Health Program | [7 empty] | lot
B.9 | Mobilization/Demobilization | [7 empty] | lot
II | WORK ITEMS
801 | Removal of Structures/Obstructions | [7 empty] | sq.m
804(a) | Embankment | [7 empty] | cu.m
804(b) | Gravel Bed | [7 empty] | cu.m
900(a) | Reinforced Concrete for Pedestal & Countertop | [7 empty] | cu.m
900(b) | Reinforced Concrete for Wall Footing | [7 empty] | cu.m
900(c) | Reinforced Concrete for Slab on Fill | [7 empty] | cu.m
1046 | Masonry Works | [7 empty] | sq.m
1027 | Cement Plaster Finish | [7 empty] | sq.m
1047 | Metal Structures | [7 empty] | kgs
1014(1)a2 | Pre-Painted Metal Sheets | [7 empty] | sq.m
1012 | Sheet Glass | [7 empty] | sq.m
1007(1)b | Aluminum Framed Glass Door | [7 empty] | sq.m
1008 | Aluminum Glass Window | [7 empty] | sq.m
1010 | Wooden Doors | [7 empty] | set
1018 | Ceramic Tiles | [7 empty] | sq.m
1032 | Painting Works | [7 empty] | sq.m
1016(1)a | Waterproofing | [7 empty] | sq.m
1003(1)a1 | Carpentry and Joinery Works (Ceiling - Fiber Cement Board) | [7 empty] | sq.m
1003(1)e2 | Carpentry and Joinery Works (Ceiling-Pre-painted Metal Panel) | [7 empty] | sq.m
1003(2) | Carpentry and Joinery Works (Cubicle Partition Wall) | [7 empty] | sq.m
1003(3) | Carpentry and Joinery Works (Cabinet) | [7 empty] | sq.m
1002 | Plumbing Works | [7 empty] | lot
1200(5) | Exhaust Fan | [7 empty] | set
SPL | Finishing Works | [7 empty] | lot
1100 | Conduit,Boxes and Fittings | [7 empty] | lot
1101 | Wire and Wiring Devices | [7 empty] | lot
1102 | Power Load Center, Switchgear and Panelboards and | [7 empty] | l.s
1103 | Lighting and Fixture Lamps | [7 empty] | l.s
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## Vicente
Contract No.
Project Title: | Repair of Vicente Trinidad National High School Gymasium, Iguig, Cagayan
[6 empty] | Municipality: |  | IGUIG, CAGAYAN
Contractor: | TS Construction |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [7 empty] | Each
B.7 | Construction Safety & Health Program | [7 empty] | L.S
B.9 | Mobilization/Demobilization | [7 empty] | L.S
II | WORK ITEMS
801(3)a | Removal of Actual Structures/Obstruction | [7 empty] | sq.m
405(1) | Structural Concrete | [7 empty] | cu.m
1032 | Painting Works | [7 empty] | sq.m
1047 | Metal Structure | [7 empty] | kg
1014 | Pre-Painted Metal Sheets | [7 empty] | sq.m
1103 | Electrical Works | [7 empty] | units
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## Budget
Contract No.
Project Title: | Improvement of Provincial Capitol, Tuguegarao City
| Improvement of Provincial Budget Office |  |  |  |  | Municipality: |  | TUGUEGARAO CITY, CAGAYAN
Contractor: | Malaya Architecture Creatives |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [7 empty] | each
B.7 | Construction safety & Health Program | [7 empty] | l.s
B.9 | Mobilization/Demobilization | [7 empty] | l.s
II | WORK ITEMS
801 | Removal of Actual Structures/Obstructions | [7 empty] | sq.m
1018 | Ceramic Tile Works | [7 empty] | sq.m
1003 | Carpentry and Joinery Works (Ceiling) | [7 empty] | sq.m
1032 | Painting, Varnishing & Other Related Works | [7 empty] | sq.m
1002 | Plumbing Works | [7 empty] | lot
1010(2)b | Doors - Wood Panel | [7 empty] | set
1007 | Aluminum Framed Glass Door | [7 empty] | sq.m
1012 | Glass and Glazing | [7 empty] | lot
1014 | Pre-Painted Metal Sheets | [7 empty] | sq.m
1000(2) | Wood Preservative | [7 empty] | sq.m
SPL-0T | Wall Finishes | [7 empty] | sq.m
1100 | Conduit, Boxes & Fittings | [7 empty] | l.s
1101 | Wires and Wiring Devices | [7 empty] | l.s
1102 | Power Load Center, Switchgear and Panelboards, and | [7 empty] | lot
Other Overcurrent Protection Devices
1103 | Lighting Fixtures and Lamps | [7 empty] | l.s
1105 | Network Cabling System | [7 empty] | lump sum
1200 | Ventilating System | [7 empty] | lump sum
1208 | Fire Alarm System | [7 empty] | lump sum
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## Accountant
Contract No.
Project Title: | Improvement of Provincial Capitol, Tuguegarao City
| Improvement of Provincial Accountant's Office |  |  |  |  | Municipality: |  | TUGUEGARAO CITY, CAGAYAN
Contractor: | Malaya Architecture Creatives |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard | [7 empty] | each
B.7 | Construction safety & Health Program | [7 empty] | l.s
B.9 | Mobilization/Demobilization | [7 empty] | lot
II | WORK ITEMS
801 | Removal of Actual Structures/Obstructions | [7 empty] | sq.m
1027(1) | Cement Plaster Finish | [7 empty] | sq.m
1046 | Masonry Works | [7 empty] | sq.m
1018 | Ceramic Tile Works | [7 empty] | sq.m
1003(1) | Carpentry and Joinery Works (Ceiling) | [7 empty] | sq.m
1032(1)a | Painting, Varnishing & Other Related Works | [7 empty] | sq.m
1002 | Plumbing Works | [7 empty] | lot
1010 | Doors | [7 empty] | set
1007 | Aluminum Framed Glass Door | [7 empty] | sq.m
1014 | Pre-Painted Metal Sheets | [7 empty] | sq.m
1012 | Glass and Glazing | [7 empty] | sq.m
1000(2) | Wood Preservative | [7 empty] | sq.m
SPL-01 | Wall Finishes | [7 empty] | sq.m
1100 | Conduit, Boxes & Fittings | [7 empty] | lot
1101 | Wires and Wiring Devices | [7 empty] | l.s
1102 | Power Load Center, Switchgear and Panelboards, and | [7 empty] | lot
Other Overcurrent, Protection Devices
1103 | Lighting Fixtures and Lamps | [7 empty] | l.s
1200(b) | Ventilating System | [7 empty] | lump sum
1208 | Fire Alarm System | [7 empty] | lump sum
1105 | Network Cabling System | [7 empty] | lot
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE

## Assessor
Contract No.
Project Title: | Improvement of Provincial Assessor's Record's Room b.) Expansion of
| Provincial Assessor's Records Room Capitol Compound, Tuguegarao City |  |  |  |  | Municipality: |  | TUGUEGARAO CITY, CAGAYAN
Contractor: | Shasha's Construction and Supply |  |  |  |  | Week Covered:
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
B.5 | Project Billboard | [7 empty] | each
B.7 | Construction Safety and Health Program | [7 empty] | lumpsum
B.9 | Mobilization/Demobilization | [7 empty] | lumpsum
1032(1) | Painting Works | [7 empty] | sq.m
1046(1) | Masonry Works | [7 empty] | sq.m
1027(1) | Cement Plaster Finish | [7 empty] | sq.m
1200(a) | Airconditioning and Ventilating System | [7 empty] | lumpsum
1003(1) | Carpentry and Joinery Works | [7 empty] | sq.m
900(1) | Reinforced Concrete for Slab on Fill | [7 empty] | cu.m
1010(2) | Doors | [7 empty] | sq.m
1007(1)a | Aluminum Framed Glass Door | [7 empty] | sq.m
1018(2) | Ceramic Tiles | [7 empty] | sq.m
804 | Embankment | [7 empty] | cu.m
1700(2) | Clearing and Grubbing | [7 empty] | lumpsum | ,
1102(1) | Panel Board with Main and Branch Breakers | [7 empty] | lumpsum
1101 | Wires and Devices | [7 empty] | lot
1103 | Lighting Fixtures and Lamps | [7 empty] | lot
1100 | Conduit, Boxes and Fittings | [7 empty] | lot
1002 | Plumbing Works | [7 empty] | lot
1005(5) | Steel Windows | [7 empty] | lumpsum
1005(6) | Window Accessories | [7 empty] | lumpsum
1003(1) | Cabinets | [7 empty] | each
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
LIZA P. NIDUA |  | DIXIE R. CABRERA |  |  | ARNOLD L. MANUEL
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
Contract No.
Project Title: | CONSTRUCTION OF LINE DRAINAGE AT REAL DE HOOD
| PROVINCIAL ROAD |  |  |  |  | Municipality: |  | CAMALANIUGAN
Contractor: | INFRAPRO CONSTRUCTION |  |  |  |  | Week Covered: |  | JUNE 17-21, 2024
ACCOMPLISHMENT
Item No. | Description |  |  | Location / Station |  |  | Quantity for the week |  | Unit
[7 empty] | Physical | Billable
FOR VARIATION ORDER
Item No. | Description |  |  | Quantity |  | Unit | Additive | Deductive | New Item
ACTIVITIES FOR THE WEEK: |  |  |  |  | FIELD INSTRUCTIONS:
PROBLEMS ENCOUNTERED/ REMARKS: |  |  |  |  | MANPOWER |  |  | EQUIPMENT
[5 empty] | Description |  | Quantity | Description | Quantity
WEEKLY PHYSICAL ACCOMPLISHMENT PERCENTAGE (CUMULATIVE):
| ORIG. TARGET | REV. TARGET | ACTUAL |  | VARIANCE |  | REMARKS
Prepared by: |  | Checked and Reviewed By: |  |  | Noted By: |  |  | Conformed by:
|  | MARK KEVIN B. MARTIN |  |  | ARNOLD L. MANUEL |  |  | ____________________________
PEO Engineer I |  | PEO Engineer II |  |  | PEO Engineer III |  |  | Contractor's Representative
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE
INSPECTION ACCOMPLISHMENT REPORT
PROVINCIAL ENGINEER'S OFFICE