## time elapse (hidden)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[8 empty] | NTP: | 2021-06-09
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED
| 2023-07-10 |  |  |  | * | To be Filled up | Note:
Project name |  | : | Construction of Abra-Baracaoit Flat Slab Bridge |  | * | To be Filled up | Just fill up those items with red boxes beside
[5 empty] | * | To be Filled up
Location |  | : | Gattaran, Cagayan |  | * | To be Filled up |  | 586
Contract Amount |  | : | 19963540.74 |  | *
Contractor |  | : | FOUR R CONSTRUCTION |  | * | To be Filled up | 267 | Days
1. | Period Covered: | : | 2021-12-01 | to |  | Don't Fill Up | Beyond the Contract Duration!!!!!!!
|  |  | 2023-07-10 |  |  | Don't Fill Up
2. | Contract Duration: | : | 320 |  | * | To be Filled up
3. | Notice to Proceed | : | 2021-11-22 |  |  | Don't Fill Up |  | 2021-12-01 | 2016-08-01 | -1948
5. | Expiry Date | : | 2022-10-16 |  |  | Don't Fill Up |  |  | 50.72 | 19
6. | Approved Time Extension | : | 132 |  | * | To be Filled up |  |  |  | -1967
12 | Approved Time Suspension | : | 135 |  | * | To be Filled up |  | 2016-08-20 | 2016-09-20 | 31
13 | Revised Contract Duration | : | 587 |  |  | Don't Fill Up |  |  |  |  | 0
14. | Revised Expiry Date due to Suspension | : | 2023-07-10 |  |  | Don't Fill Up
15. | Total Calendar days Elapsed to Date | : | 587 |  |  | Don't Fill Up
16 | Percentage Of work accomplished-Actual | : | 57.07% |  | * | To be Filled up
17. | Percentage Of work accomplished-Planned | : | 100% |  |  | Don't Fill Up |  | 0.87507
18 | Slippage | : | -42.93% |  |  | Don't Fill Up
19. | Remarks | : |  |  | * | To be Filled up |  | -42.93%
90.45
30.61
Submitted by: | [7 empty] | 2015-07-15 | -2331
529
MA. VICTORIA E. REYES
Engineer II
1283860.56
[8 empty] | Liquidation Damages: | 147163.5053 |  | 0
2016-03-31
285
2017-01-10
13+
as of

## time elapse (2) (hidden)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[8 empty] | NTP: | 2021-06-09
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED
| 2026-06-10 |  |  |  | * | To be Filled up | Note:
Project name |  | : | Construction of Abra-Baracaoit Flat Slab Bridge |  | * | To be Filled up | Just fill up those items with red boxes beside
[5 empty] | * | To be Filled up
Location |  | : | Gattaran, Cagayan |  | * | To be Filled up |  | 1652
Contract Amount |  | : | 19963540.74 |  | *
Contractor |  | : | FOUR R CONSTRUCTION |  | * | To be Filled up | 1333 | Days
1. | Period Covered: | : | 2021-12-01 | to |  | Don't Fill Up | Beyond the Contract Duration!!!!!!!
|  |  | 2026-06-10 |  |  | Don't Fill Up
2. | Contract Duration: | : | 320 |  | * | To be Filled up
3. | Notice to Proceed | : | 2021-11-22 |  |  | Don't Fill Up |  | 2021-12-01 | 2016-08-01 | -1948
5. | Expiry Date | : | 2022-10-16 |  |  | Don't Fill Up |  |  | 50.72 | 19
6. | Approved Time Extension | : | 132 |  | * | To be Filled up |  |  |  | -1967
12 | Approved Time Suspension | : | 135 |  | * | To be Filled up |  | 2016-08-20 | 2016-09-20 | 31
13 | Revised Contract Duration | : | 587 |  |  | Don't Fill Up |  |  |  |  | 1066
14. | Revised Expiry Date due to Suspension | : | 2023-07-10 |  |  | Don't Fill Up
15. | Total Calendar days Elapsed to Date | : | 1653 |  |  | Don't Fill Up
16 | Percentage Of work accomplished-Actual | : | #REF! |  | * | To be Filled up
17. | Percentage Of work accomplished-Planned | : | 100% |  |  | Don't Fill Up |  | 0.6335
18 | Slippage | : | #REF! |  |  | Don't Fill Up
19. | Remarks | : |  |  | * | To be Filled up |  | #REF!
90.45
30.61
Submitted by: | [7 empty] | 2015-07-15 | -2331
529
MA. VICTORIA E. REYES
Engineer II
1283860.56
[8 empty] | Liquidation Damages: | #REF! |  | #REF!
2016-03-31
285
2017-01-10
13+
as of

## stewa(EXPIRY) (hidden)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2023-07-10 |  |  |  | To be Filled In | 2023-07-10 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | #REF! |  | To be Filled In | #REF! | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | #REF! |  | To be Filled In | #REF! | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | #REF! |  | To be Filled In | #REF! | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | FOUR R CONSTRUCTION |  | To be Filled In | FOUR R CONSTRUCTION | Contractor
1. | Period Covered: | : | 2021-12-02 | to
2023-07-10
2. | Contract Duration | : | 320 |  | To be Filled In | 320 | Contract Duration
3. | Date of Receipt of Notice to Proceed | : | 2021-11-22 |  | To be Filled In | 2021-11-22 | Date of Receipt of Notice to Proceed
4. | Expiry Date | : | 2022-10-16
5. | Approved Time Extension | : | 267 |  | To be Filled In | 132 | Approved Time Extension
6. | Approved Time Suspension | : | 135 |  | To be Filled In | 135 | Approved Time Suspension
7. | Total Time Extension |  | 267 |  | Don't Fill In | 267 | Total Time Extension
8. | Revised Contract Duration | : | 586 |  | Don't Fill In | 586 | Revised Contract Duration
9. | Revised Expiry Date | : | 2023-07-10
10. | Total Calendar days Elapsed to Date | : | 586
11. | Percentage of work accomplished - Actual | : | 57.07% |  |  | 57.07% | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 100% |  | Don't Fill In | 6.863% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | -42.93% |  | Don't Fill In | 100% | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | :
[5 empty] | Don't Fill In | 183.1% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| MA. VICTORIA E. REYES |  | ARNOLD L. MANUEL
| Engineer II |  | OIC Chief - Construction Division
As of

## SWA (hidden)
STATEMENT OF WORK ACCOMPLISHMENT
As of July 10, 2023 (expiry date)
Project Title: | Construction of Abra-Baracaoit Flat Slab Bridge
Location: | Gonzaga, Cagayan
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS | #REF! | #REF! |  |  | less
|  |  | ORIGINAL | [9 empty] | 650 | 1320 | 660 | contract |  | adj. amount
PART A | FACILITIES FOR ENGINEERS
A.1.1 (8) | Provision of Field Office for the Engineer (Rental Basis) |  | 10.67 | mo | 5775 | 61619.25 | 0.309% | 49295.4 | 0 | 49295.4 | 0.247% | On-going | 28297.5
PART B | OTHER GENERAL REQUIREMENTS
B.5 | Billboards and Signages |  | 2 | each | 11655 | 23310 | 0.117% | 11655 | 0 | 11655 | 0.058% | On-going
B.7 | Construction Safety and Health Program |  | all | l.s | 49665 | 49665 | 0.249% | 39732 | 0 | 39732 | 0.199% | On-going | 24832.5
B.9 | Mobilization/ Demobilization |  | all | l.s | 175000 | 175000 | 0.877% | 87500 | 0 | 87500 | 0.438% | On-going
I | ROAD
PART C | EARTHWORKS
102(2) | Roadway Excavation (Surplus Common Materials) |  | 1871.15 | cu.m | 142.59 | 266807.28 | 1.336% | 186765.1 | 0 | 186765.1 | 0.936% | On-going
104(1)a | Embankment |  | 743.28 | cu.m | 111.2 | 82652.74 | 0.414% | 57856.92 | 0 | 57856.92 | 0.29% | On-going | 41326.368
105(1) | Sub-Grade Preparation (Common Materials) |  | 2481.5 | sq.m | 17.44 | 43277.36 | 0.217% | 30294.15 | 0 | 30294.15 | 0.152% | On-going | 21638.68
PART D | SUBBASE COURSE
200(1) | Aggregate Sub-base Course |  | 760.33 | cu.m | 684.79 | 520666.38 | 2.608% | 225764.99 | 0 | 225764.99 | 1.131% | On-going | 260333.1903 | 0.8 |  | 520666.3807 | 0 | 520666.3807 | 40384.71
PART E | SURFACE COURSE | [12 empty] | 0.8 |  | 0 | 0 | 0 | 23203.8
0 | Mobilization/ Demobilization |  | 1772.5 | sq.m | 1248.35 | 2212700.38 | 11.08% | 1106350.19 | 0 | 0 | 7.793% | On-going | 1555756.1875 | 177.25 |  | 2212700.375 | 0 | 2212700.375 | 61058.41
II | CONSTRUCTION OF BRIDGE (FLAT SLAB) | [14 empty] | 0 | 0 | 0 | 1127300.56
A | EARTHWORKS | [14 empty] | 0 | 0 | 0 | 3199178.36
103(1)a | Structure Excavation |  | 83.28 | cu.m | 127.85 | 10647.35 | 0.053% |  |  |  | 0% | not yet started | 10647.35
B.18 | Craneway |  | all | l.s | 3120000 | 3120000 | 15.63% | 2340000 | 0 | 2340000 | 11.72% | On-going | 3120000
B | SUB-STRUCTURE
404(4)a | Precast Concrete Piles, Furnished |  | 784 | ln.m | 5449.5 | 4272408 | 21.4% | 3269700 | 0 | 3269700 | 16.38% | On-going | 3269700 | 600
400(14) | Precast Concrete Piles, Driven |  | 539 | ln.m | 2106.23 | 1135257.97 | 5.687% | 631869 | 0 | 631869 | 3.165% | On-going | 631869
400(16)a | Test Piles, furnished and Driven (400mmx400mm) |  | 16 | ln.m | 7308 | 116928 | 0.586% | 109620 | 0 | 109620 | 0.549% | On-going | 116928 |  |  | 116928 | 0 | 116928 | 32303.68
C | SUPERSTRUCTURE | [14 empty] | 0 | 0 | 0 | 23203.8
404(1)b | Reinforcing Steel Bars |  | 35236.81 | kg. | 90.34 | 3183293.42 | 15.95% | 1206153.94 | 257063.1652 | 1463217.1052 | 7.329% | On-going | 1463217.1052 | 4740.195 | 691 | 4049.195 | 0 | 4049.195 | 61058.41
405(1)b | Structural Concrete Class A-Bridge Superstructure 27 Mpa |  | 250.79 | cu.m | 10432.84 | 2616451.94 | 13.11% | 735723.88 | 598406.8335 | 1334130.7135 | 6.683% | On-going | 1334130.7135 | 26.132
D | SLOPE PROTECTION | [12 empty] | 4.672
404(1)a | Reinforcing Steel Bars |  | 7375.11 | kg. | 88.98 | 656237.29 | 3.287% |  |  | 0 | 0% | not yet started
405(1)a | Structural Concrete Class A 20.7 Mpa |  | 136.68 | cu.m | 6860.58 | 937704.07 | 4.697% |  |  | 0 | 0% | not yet started
E | BRIDGE APPROACH | [14 empty] | 0 | 0 | 0 | 1127300.56
404(1)a | Reinforcing Steel Bars |  | 3194.34 | kg. | 100.33 | 320488.13 | 1.605% |  |  | 0 | 0% | not yet started | 11 |  |  | 320488.1322 | 0 | 320488.1322 | 3199178.36
405(1)a | Structural Concrete Class A 20.7 Mpa |  | 18.71 | cu.m | 8467.46 | 158426.18 | 0.794% |  |  | 0 | 0% | not yet started
T O T A L S | [5 empty] | 19963540.74 | 100% | 9625181.99 | 855469.9987 | 11393156.5634 | 57.07% |  |  |  |  | 3174832.0829 | 0 | 3174832.0829 | 8894170.65
0
3174832.0829
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 57.07% | [7 empty] | -3174832.0829
[5 empty] | TOTAL PROJECT COST |  |  | 19963540.74
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 855469.9987
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 855469.9987
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
MA. VICTORIA E. REYES |  | ARNOLD L. MANUEL |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | MANUEL N. MAMBA, M.D.
Engineer II |  | OIC- Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
STATEMENT OF WORK ACCOMPLISHMENT
As of _____________________, 2020
A. | CONCRETING OF FARM TO MARKET ROAD ZIMINILA
CAMALANIUGAN, CAGAYAN
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
|  |  | ORIGINAL | [13 empty] | 16%
105(1) | Sub Grade Preparation |  | 1075.8 | sq.m. | 102.17 | 109364.91 | 10.0228 |  |  | 0 | #REF! | on-going |  |  |  | 109914.486 | 17586.3178 | 92328.1682
200(1) | Aggregate Sub Base Coarse |  | 173.25 | sq.m. | 804.58 | 223636.89 | 20.4954 |  |  | 0 | 0% | on-going |  |  |  | 139393.485 | 22302.9576 | 117090.5274
311(1)C | PCCP |  | 660 | sq.m. | 72.96 | 672973.03 | 61.6752 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 48153.6 | 7704.576 | 40449.024
B.9 | Mobilization/ Demobilization |  | 1 | l/s | 128.93 | 25951.88 | 2.3784 |  |  | 0 | 0% | on-going |  | 604.87 | #REF! | 128.93 | 20.6288 | 108.3012
B.5 | Billboards and Signages |  | 2 | each | 18.37 | 10196.76 | 0.93449 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 36.74 | 5.8784 | 30.8616
B.7 | Occupational Health and Safety |  | 1 | l/s | 1208.89 | 28041.09 | 2.5698 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 1208.89 | 193.4224 | 1015.4676
A.1.1(8a) | Provisions of Field Office for the Engineer |  | 1.83 | mos | 1291.19 | 20992.58 | 1.9239 |  |  | 0 | 0% | on-going |  | 1067.5 |  | 2362.8777 | 378.0604 | 1984.8173
T O T A L S | [5 empty] | 1091157.14 | 100 | 0 | 0 | 0 | #REF! |  |  |  |  | 301199.0087 | 48191.8414 | 253007.1673
[14 empty] | #REF! |  | 1957.7936
299241.2151
[5 empty] | % THIS ACCOMPLISHMENT |  |  | #REF! |  | %
[5 empty] | TOTAL PROJECT COST |  |  | 1091157.14
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 0
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 0
Requested by: |  | Prepared by: |  |  | Checked by: |  |  |  | Approved:
EV INTERIOR CONSTRUCTION |  | MARISSA A. MACADANGDANG |  |  | MA. VICTORIA E. REYES |  |  |  | MANUEL N. MAMBA, M.D.
Contractor |  | Engineering Assistant |  |  | Engineer II |  |  |  | Governor

## STEWA (02-20-26)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2026-02-27 |  |  |  | To be Filled In | 2026-02-27 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | REPAIR OF VICENTE TRINIDAD NATIONAL HIGH SCHOOL GYMNASIUM, IGUIG, CAGAYAN |  | To be Filled In | REPAIR OF VICENTE TRINIDAD NATIONAL HIGH SCHOOL GYMNASIUM, IGUIG, CAGAYAN | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Iguig, Cagayan |  | To be Filled In | Iguig, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 2396212.4 |  | To be Filled In | 2396212.4 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | TS Construction |  | To be Filled In | TS Construction | Contractor
1. | Period Covered: | : | 2025-08-23 | to
2026-02-27
2. | Contract Duration | : | 144 |  | To be Filled In | 144 | Contract Duration
3. | Date of Receipt of Notice to Proceed | : | 2025-08-14 |  | To be Filled In | 2025-08-14 | Date of Receipt of Notice to Proceed
4. | Expiry Date | : | 2026-01-14
5. | Approved Time Extension | : | 47 |  | To be Filled In | 47 | Approved Time Extension
6. | Approved Time Suspension | : | 0 |  | To be Filled In |  | Approved Time Suspension
7. | Total Time Extension |  | 47 |  | Don't Fill In | 47 | Total Time Extension
8. | Revised Contract Duration | : | 191 |  | Don't Fill In | 191 | Revised Contract Duration
9. | Revised Expiry Date | : | 2026-03-02
10. | Total Calendar days Elapsed to Date | : | 188
11. | Percentage of work accomplished - Actual | : | #REF! |  |  | #REF! | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 100% |  | Don't Fill In | 78.68% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | #REF! |  | Don't Fill In | 100% | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | :
[5 empty] | Don't Fill In | 130.6% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| DIXIE R. CABRERA |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
As of

## STEWA (July 26, 2024) (hidden)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| July 26, 2024 |  |  |  | To be Filled In | July 26, 2024 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | Construction of Multi-Purpose Building Lallo National High School |  | To be Filled In | Construction of Multi-Purpose Building Lallo National High School | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Lallo, Cagayan |  | To be Filled In | Lallo, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3796932.5 |  | To be Filled In | 3796932.5 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Rucs Konsult and Construction Services |  | To be Filled In | Rucs Konsult and Construction Services | Contractor
1. | Period Covered: | : | 2023-04-29 | to
July 26, 2024
2. | Contract Duration | : | 180 |  | To be Filled In | 180 | Contract Duration
3. | Date of Receipt of Notice to Proceed | : | 2023-04-20 |  | To be Filled In | 2023-04-20 | Date of Receipt of Notice to Proceed
4. | Expiry Date | : | 2023-10-26
5. | Approved Time Extension | : | 0 |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 446 |  | To be Filled In | 450 | Approved Time Suspension
7. | Total Time Extension |  | 0 |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | -1 | Revised Contract Duration
9. | Revised Expiry Date | : | 2025-01-14
10. | Total Calendar days Elapsed to Date | : | 455
11. | Percentage of work accomplished - Actual | : | #REF! |  |  | #REF! | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 54.36% |  | Don't Fill In | 54.36% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | #REF! |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | :
[5 empty] | Don't Fill In | 252.8% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| MARK KEVIN B. MARTIN |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
As of

## STEWA (August 16, 2024) (hidden)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2024-09-06 |  |  |  | To be Filled In | 2024-09-06 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | Construction of Multi-Purpose Building Lallo National High School |  | To be Filled In | Construction of Multi-Purpose Building Lallo National High School | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Lallo, Cagayan |  | To be Filled In | Lallo, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3796932.5 |  | To be Filled In | 3796932.5 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Rucs Konsult and Construction Services |  | To be Filled In | Rucs Konsult and Construction Services | Contractor
1. | Period Covered: | : | 2023-04-29 | to
2024-09-06
2. | Contract Duration | : | 180 |  | To be Filled In | 180 | Contract Duration
3. | Date of Receipt of Notice to Proceed | : | 2023-04-20 |  | To be Filled In | 2023-04-20 | Date of Receipt of Notice to Proceed
4. | Expiry Date | : | 2023-10-26
5. | Approved Time Extension | : | 0 |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 446 |  | To be Filled In | 450 | Approved Time Suspension
7. | Total Time Extension |  | 0 |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | -1 | Revised Contract Duration
9. | Revised Expiry Date | : | 2025-01-14
10. | Total Calendar days Elapsed to Date | : | 51
11. | Percentage of work accomplished - Actual | : | #REF! |  |  | #REF! | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 18.53% |  | Don't Fill In | 18.53% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | #REF! |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | :
[5 empty] | Don't Fill In | 28.33% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| MARK KEVIN B. MARTIN |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
As of

## SWA (August 23, 2024) (hidden)
STATEMENT OF WORK ACCOMPLISHMENT
[5 empty] | As of | 2024-09-06
Project Title: | Construction of Multi-Purpose Building Lallo National High School
Location: | Lallo, Cagayan
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/ |  |  | 802 | Excavation
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS | #REF! |  | Length | Width | Height | Qty | Volume | Unit
|  |  | ORIGINAL | [9 empty] | 650 |  | 1.5 | 1.5 | 1.5 | 4 | 13.5 | cu.m
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | each | 14849.21 | 29698.42 | 0.744% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF! |  | 804(b) | Gravel Bedding
B.7 | Construction Safety and Health Program |  | 1 | l.s | 52524.01 | 52524.01 | 1.316% | #REF! | #REF! | 2501.1433 | 0.063% | On going | #REF! |  | Length | Width | Thickness | Qty | Volume | Unit
B.9 | Mobilization/ Demobilization |  | 1 | l.s | 31020.38 | 31020.38 | 0.777% | #REF! | #REF! | 15510.19 | 0.389% | On going | #REF! |  | 1.5 | 1.5 | 0.1 |  | 0 | cu.m
II | WORK ITEMS
802 | Excavation |  | 92.65 | cu.m | 221.94 | 20562.74 | 0.515% | #REF! | 2996.19 | 8225.096 | 0.206% | On going | 13.5 |  | 900 (a) | Reinforced Concrete Column Footing
804(a) | Backfilling |  | 32.4 | cu.m | 55.17 | 1787.51 | 0.045% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF! |  | Length | Width | Thickness | Qty | Volume | Unit
804(b) | Gravel Bedding |  | 54.66 | cu.m | 813.59 | 44470.83 | 1.114% | #REF! | 0 |  | 0% | Not Yet Started | 0 |  | 1.5 | 1.5 | 0.35 |  | 0 | sq.m.
900 (a) | Reinforced Concrete Column Footing |  | 9.45 | cu.m | 16311.68 | 154145.38 | 3.862% | #REF! | 0 |  | 0% | Not Yet Started | 0
901 (b) | Reinforced Concrete Wall Footing |  | 3.12 | cu.m | 17371.06 | 54197.71 | 1.358% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
902 (c) | Reinforced Concrete Column and Corbel |  | 16.32 | cu.m | 22958.55 | 374683.54 | 9.389% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
903 (d) | Reinforced Concrete Beams |  | 5.6 | cu.m | 26671.53 | 149360.57 | 3.743% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
904 (e) | Reinforced Concrete Slab |  | 50.4 | cu.m | 9441 | 475826.4 | 11.92% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
903 | Formworks and Falseworks |  | 108 | sq.m. | 3583.04 | 386968.32 | 9.696% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
1046 | Masonry Works |  | 36.8 | sq.m. | 968.36 | 35635.65 | 0.893% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
1027 | Cement Plaster Finish |  | 212.76 | sq.m. | 55.61 | 11831.58 | 0.296% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
1032 | Painting Works |  | 194.36 | sq.m. | 358.8 | 69736.37 | 1.747% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
1047 | Metal Structure |  | 16113.92 | kgs. | 90.41 | 1456859.51 | 36.5% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
1013(a) | Corrugated Asphalt Roof |  | 684 | sq.m. | 793.5 | 542754 | 13.6% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
1103 | Electrical Works |  | 12 | units | 8231.21 | 98774.52 | 2.475% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
T O T A L S | [5 empty] | 3990837.44 | 100% |  | #REF! | 26236.4293 | 0.658%
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 0.658%
[5 empty] | TOTAL PROJECT COST |  |  | 3990837.44
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | #REF!
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | #REF!
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
MARK KEVIN B. MARTIN |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | MANUEL N. MAMBA, M.D.
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
STATEMENT OF WORK ACCOMPLISHMENT
As of _____________________, 2020
A. | CONCRETING OF FARM TO MARKET ROAD ZIMINILA
CAMALANIUGAN, CAGAYAN
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
|  |  | ORIGINAL | [13 empty] | 16%
105(1) | Sub Grade Preparation |  | 1075.8 | sq.m. | 102.17 | 109364.91 | 10.0228 |  |  | 0 | #REF! | on-going |  |  |  | 109914.486 | 17586.3178 | 92328.1682
200(1) | Aggregate Sub Base Coarse |  | 173.25 | sq.m. | 804.58 | 223636.89 | 20.4954 |  |  | 0 | 0% | on-going |  |  |  | 139393.485 | 22302.9576 | 117090.5274
311(1)C | PCCP |  | 660 | sq.m. | 72.96 | 672973.03 | 61.6752 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 48153.6 | 7704.576 | 40449.024
B.9 | Mobilization/ Demobilization |  | 1 | l/s | 128.93 | 25951.88 | 2.3784 |  |  | 0 | 0% | on-going |  | 604.87 | #REF! | 128.93 | 20.6288 | 108.3012
B.5 | Billboards and Signages |  | 2 | each | 18.37 | 10196.76 | 0.93449 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 36.74 | 5.8784 | 30.8616
B.7 | Occupational Health and Safety |  | 1 | l/s | 1208.89 | 28041.09 | 2.5698 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 1208.89 | 193.4224 | 1015.4676
A.1.1(8a) | Provisions of Field Office for the Engineer |  | 1.83 | mos | 1291.19 | 20992.58 | 1.9239 |  |  | 0 | 0% | on-going |  | 1067.5 |  | 2362.8777 | 378.0604 | 1984.8173
T O T A L S | [5 empty] | 1091157.14 | 100 | 0 | 0 | 0 | #REF! |  |  |  |  | 301199.0087 | 48191.8414 | 253007.1673
[14 empty] | #REF! |  | 1957.7936
299241.2151
[5 empty] | % THIS ACCOMPLISHMENT |  |  | #REF! |  | %
[5 empty] | TOTAL PROJECT COST |  |  | 1091157.14
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 0
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 0
Requested by: |  | Prepared by: |  |  | Checked by: |  |  |  | Approved:
EV INTERIOR CONSTRUCTION |  | MARISSA A. MACADANGDANG |  |  | MA. VICTORIA E. REYES |  |  |  | MANUEL N. MAMBA, M.D.
Contractor |  | Engineering Assistant |  |  | Engineer II |  |  |  | Governor

## STEWA (August 23, 2024) (hidden)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2024-08-23 |  |  |  | To be Filled In | 2024-08-23 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | Construction of Multi-Purpose Building Lallo National High School |  | To be Filled In | Construction of Multi-Purpose Building Lallo National High School | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Lallo, Cagayan |  | To be Filled In | Lallo, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3990443.93 |  | To be Filled In | 3990443.93 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | RUCS Construction |  | To be Filled In | RUCS Construction | Contractor
1. | Period Covered: | : | 2024-08-07 | to
2024-08-23
2. | Contract Duration | : | 210 |  | To be Filled In | 210 | Contract Duration
3. | Date of Receipt of Notice to Proceed | : | 2024-07-29 |  | To be Filled In | 2024-07-29 | Date of Receipt of Notice to Proceed
4. | Expiry Date | : | 2025-03-05
5. | Approved Time Extension | : | 0 |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 0 |  | To be Filled In |  | Approved Time Suspension
7. | Total Time Extension |  | 0 |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | -1 | Revised Contract Duration
9. | Revised Expiry Date | : | 0
10. | Total Calendar days Elapsed to Date | : | 17
11. | Percentage of work accomplished - Actual | : | #REF! |  |  | #REF! | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 1.608% |  | Don't Fill In | 1.608% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | #REF! |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | :
[5 empty] | Don't Fill In | 8.095% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| MARK KEVIN B. MARTIN |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
As of

## SWA (August 30, 2024) (hidden)
STATEMENT OF WORK ACCOMPLISHMENT
[5 empty] | As of | 2024-08-30
Project Title: | Construction of Multi-Purpose Building Lallo National High School
Location: | Lallo, Cagayan
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/ |  |  | 802 | Excavation
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS | #REF! |  | Length | Width | Height | Qty | Volume | Unit
|  |  | ORIGINAL | [9 empty] | 650 |  | 1.5 | 1.5 | 1.5 | 4 | 13.5 | cu.m
I | OTHER GENERAL REQUIREMENTS
B.5 | Project Billboard |  | 2 | each | 14849.21 | 29698.42 | 0.744% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF! |  | 804(b) | Gravel Bedding
B.7 | Construction Safety and Health Program |  | 1 | l.s | 52524.01 | 52524.01 | 1.316% | #REF! | #REF! | 2501.1433 | 0.063% | On going | #REF! |  | Length | Width | Thickness | Qty | Volume | Unit
B.9 | Mobilization/ Demobilization |  | 1 | l.s | 31020.38 | 31020.38 | 0.777% | #REF! | #REF! | 15510.19 | 0.389% | On going | #REF! |  | 1.5 | 1.5 | 0.1 |  | 0 | cu.m
II | WORK ITEMS
802 | Excavation |  | 92.65 | cu.m | 221.94 | 20562.74 | 0.515% | #REF! | 2996.19 | 8225.096 | 0.206% | On going | 13.5 |  | 900 (a) | Reinforced Concrete Column Footing
804(a) | Backfilling |  | 32.4 | cu.m | 55.17 | 1787.51 | 0.045% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF! |  | Length | Width | Thickness | Qty | Volume | Unit
804(b) | Gravel Bedding |  | 54.66 | cu.m | 813.59 | 44470.83 | 1.114% | #REF! | 0 |  | 0% | Not Yet Started | 0 |  | 1.5 | 1.5 | 0.35 |  | 0 | sq.m.
900 (a) | Reinforced Concrete Column Footing |  | 9.45 | cu.m | 16311.68 | 154145.38 | 3.862% | #REF! | 0 |  | 0% | Not Yet Started | 0
901 (b) | Reinforced Concrete Wall Footing |  | 3.12 | cu.m | 17371.06 | 54197.71 | 1.358% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
902 (c) | Reinforced Concrete Column and Corbel |  | 16.32 | cu.m | 22958.55 | 374683.54 | 9.389% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
903 (d) | Reinforced Concrete Beams |  | 5.6 | cu.m | 26671.53 | 149360.57 | 3.743% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
904 (e) | Reinforced Concrete Slab |  | 50.4 | cu.m | 9441 | 475826.4 | 11.92% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
903 | Formworks and Falseworks |  | 108 | sq.m. | 3583.04 | 386968.32 | 9.696% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
1046 | Masonry Works |  | 36.8 | sq.m. | 968.36 | 35635.65 | 0.893% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
1027 | Cement Plaster Finish |  | 212.76 | sq.m. | 55.61 | 11831.58 | 0.296% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
1032 | Painting Works |  | 194.36 | sq.m. | 358.8 | 69736.37 | 1.747% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
1047 | Metal Structure |  | 16113.92 | kgs. | 90.41 | 1456859.51 | 36.5% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
1013(a) | Corrugated Asphalt Roof |  | 684 | sq.m. | 793.5 | 542754 | 13.6% | #REF! | #REF! | 0 | 0% | Not Yet Started | #REF!
1103 | Electrical Works |  | 12 | units | 8231.21 | 98774.52 | 2.475% | #REF! | #REF! |  | 0% | Not Yet Started | #REF!
T O T A L S | [5 empty] | 3990837.44 | 100% |  | #REF! | 26236.4293 | 0.658%
[5 empty] | % THIS ACCOMPLISHMENT |  |  | 0.658%
[5 empty] | TOTAL PROJECT COST |  |  | 3990837.44
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | #REF!
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | #REF!
Prepared by: |  | Checked by: |  |  |  | Recommending Approval: |  |  |  | Approved:
MARK KEVIN B. MARTIN |  | KATHLEEN MEI P. BAGASIN |  |  |  | KINGSTON JAMES S. DELA CRUZ |  |  |  | MANUEL N. MAMBA, M.D.
Engineer II |  | Chief of Construction Division |  |  |  | Provincial Engineer |  |  |  | Governor
STATEMENT OF WORK ACCOMPLISHMENT
As of _____________________, 2020
A. | CONCRETING OF FARM TO MARKET ROAD ZIMINILA
CAMALANIUGAN, CAGAYAN
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
|  |  | ORIGINAL | [13 empty] | 16%
105(1) | Sub Grade Preparation |  | 1075.8 | sq.m. | 102.17 | 109364.91 | 10.0228 |  |  | 0 | #REF! | on-going |  |  |  | 109914.486 | 17586.3178 | 92328.1682
200(1) | Aggregate Sub Base Coarse |  | 173.25 | sq.m. | 804.58 | 223636.89 | 20.4954 |  |  | 0 | 0% | on-going |  |  |  | 139393.485 | 22302.9576 | 117090.5274
311(1)C | PCCP |  | 660 | sq.m. | 72.96 | 672973.03 | 61.6752 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 48153.6 | 7704.576 | 40449.024
B.9 | Mobilization/ Demobilization |  | 1 | l/s | 128.93 | 25951.88 | 2.3784 |  |  | 0 | 0% | on-going |  | 604.87 | #REF! | 128.93 | 20.6288 | 108.3012
B.5 | Billboards and Signages |  | 2 | each | 18.37 | 10196.76 | 0.93449 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 36.74 | 5.8784 | 30.8616
B.7 | Occupational Health and Safety |  | 1 | l/s | 1208.89 | 28041.09 | 2.5698 |  |  | 0 | 0% | on-going |  | #REF! | #REF! | 1208.89 | 193.4224 | 1015.4676
A.1.1(8a) | Provisions of Field Office for the Engineer |  | 1.83 | mos | 1291.19 | 20992.58 | 1.9239 |  |  | 0 | 0% | on-going |  | 1067.5 |  | 2362.8777 | 378.0604 | 1984.8173
T O T A L S | [5 empty] | 1091157.14 | 100 | 0 | 0 | 0 | #REF! |  |  |  |  | 301199.0087 | 48191.8414 | 253007.1673
[14 empty] | #REF! |  | 1957.7936
299241.2151
[5 empty] | % THIS ACCOMPLISHMENT |  |  | #REF! |  | %
[5 empty] | TOTAL PROJECT COST |  |  | 1091157.14
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  | 0
|  |  |  | Less: | MOBILIZATION
[5 empty] | TOTAL THIS VOUCHER |  |  | 0
Requested by: |  | Prepared by: |  |  | Checked by: |  |  |  | Approved:
EV INTERIOR CONSTRUCTION |  | MARISSA A. MACADANGDANG |  |  | MA. VICTORIA E. REYES |  |  |  | MANUEL N. MAMBA, M.D.
Contractor |  | Engineering Assistant |  |  | Engineer II |  |  |  | Governor

## STEWA (August 30, 2024) (hidden)
Republic of the Philippines
PROVINCE OF CAGAYAN
Capitol Hills, Tuguegarao City
PROVINCIAL ENGINEER'S OFFICE
[5 empty] | JUST FILL IN ON BLUE CELL!!! |  |  | LEGEND:
STATEMENT OF TIME ELAPSED AND WORK ACCOMPLISHED | [7 empty] | single | WITHOUT REVISION
[8 empty] | in a relationship | WITH REVISION
| 2024-08-30 |  |  |  | To be Filled In | 2024-08-30 |  | complicated | ON THE EXPIRY DATE WITHOUT REVISION
[8 empty] | married | ON THE EXPIRY DATE WITH REVISION
[8 empty] | separated | ON THE COMPLETION DATE WITHOUT REVISION
Project Name |  | : | Construction of Multi-Purpose Building Lallo National High School |  | To be Filled In | Construction of Multi-Purpose Building Lallo National High School | Project Name | divorced | ON THE COMPLETION DATE WITH REVISION
Location |  | : | Lallo, Cagayan |  | To be Filled In | Lallo, Cagayan | Location | LDR_1 | WITHOUT REVISION
Contract Amount |  | : | 3796932.5 |  | To be Filled In | 3796932.5 | Contract Amount | LDR_2 | WITH REVISION
Contractor |  | : | Rucs Konsult and Construction Services |  | To be Filled In | Rucs Konsult and Construction Services | Contractor
1. | Period Covered: | : | 2023-04-29 | to
2024-08-30
2. | Contract Duration | : | 180 |  | To be Filled In | 180 | Contract Duration
3. | Date of Receipt of Notice to Proceed | : | 2023-04-20 |  | To be Filled In | 2023-04-20 | Date of Receipt of Notice to Proceed
4. | Expiry Date | : | 2023-10-26
5. | Approved Time Extension | : | 0 |  | To be Filled In |  | Approved Time Extension
6. | Approved Time Suspension | : | 446 |  | To be Filled In | 446 | Approved Time Suspension
7. | Total Time Extension |  | 0 |  | Don't Fill In | 0 | Total Time Extension
8. | Revised Contract Duration | : | 0 |  | Don't Fill In | -1 | Revised Contract Duration
9. | Revised Expiry Date | : | 2025-01-14
10. | Total Calendar days Elapsed to Date | : | 44
11. | Percentage of work accomplished - Actual | : | #REF! |  |  | 0.658% | (FROM SWA)
12. | Percentage of work accomplished -Planned | : | 14.03% |  | Don't Fill In | 14.03% | W/ FORMULA - Planned (WITHOUT time extension)
13. | Slippage | : | #REF! |  | Don't Fill In |  | W/ FORMULA - Planned (WITH time extension)
14. | Remarks | :
[5 empty] | Don't Fill In | 24.44% | LINEAR - Planned (WITHOUT time extension)
[5 empty] | Don't Fill In | 100% | LINEAR - Planned (WITH time extension)
| Submitted by: |  | Noted by: |  | F | WRITE "F" - OPT TO USE FORMULA
WRITE "L" - OPT TO USE LINEAR
| MARK KEVIN B. MARTIN |  | KATHLEEN MEI P. BAGASIN
| Engineer II |  | Engineer IV (Chief-Construction Division)
As of

## swa_BC (hidden)
STATEMENT OF WORK ACCOMPLISHMENT
Improvement of Road along Sta. Cruz - Cabiraoan Provincial Road - Concreting of Road with Box Culvert
Gonzaga, Cagayan
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
|  |  | ORIGINAL | [11 empty] | 497476.03
| Project Billboard |  | 230 | sq.m | 50.74 | 11670.2 | 1.185% |  | 11670.2 | 11670.2 | 1.185% | COMPLETED |  | 1.42% | 7064.16 | 30.7137 | 7064.16
| Construction Safety and Health Program |  | 46 | cu.m | 979.58 | 45060.68 | 4.575% |  | 45060.68 | 45060.68 | 4.575% | COMPLETED |  | 1.42% | 7064.16 | 153.5687 | 7064.16
| Mobilization/ Demobilization |  | 230 | sq.m | 1360.32 | 312873.6 | 31.77% |  | 312873.6 | 312873.6 | 31.77% | COMPLETED |  | 64.23% | 319528.854 | 1389.2559 | 319528.85
| Removal of Existing Concrete Pavement |  | 64.8 | cu.m | 169.17 | 10962.22 | 1.113% |  | 10962.22 | 10962.22 | 1.113% | COMPLETED |  | 28.57% | 142128.902 | 2193.3472 | 142128.9
| Removal of Actual Structures/Obstruction (610mmØ RCPC) |  | 3021.44 | kg | 76.22 | 230294.16 | 23.38% |  | 230294.16 | 230294.16 | 23.38% | COMPLETED |  | 2.54% | 12635.891 | 4.1821 | 12635.9
| Roadway Excavation (Surplus Common Excavation) |  | 36 | cu.m | 7119 | 256284 | 26.02% |  | 256284 | 256284 | 26.02% | COMPLETED |  | 1.03% | 5124.003 | 142.3334 | 5124
| Structure Excavation |  | 46 | ln.m | 1607.18 | 73930.28 | 7.506% |  | 73930.28 | 73930.28 | 7.506% | COMPLETED |  | 0.79% | 3930.061 | 85.4361 | 3930.06
| Pipe Culvert and Drain Excavation |  | 1 | ls | 6825 | 6825 | 0.693% |  | 6825 | 6825 | 0.693% | COMPLETED |  | 2.54% | 12635.891 | 12635.891 | 12635.89
| Embankment (From Roadway Excavation) |  | 1 | ls | 12726 | 12726 | 1.292% |  | 12726 | 12726 | 1.292% | COMPLETED |  | 1.03% | 5124.003 | 5124.003 | 5124
| Sub-grade Preparation (Common Materials) |  | 2.5 | mos | 5197.5 | 12993.75 | 1.319% |  | 12993.75 | 12993.75 | 1.319% | COMPLETED |  | 0.79% | 3930.061 | 1572.0244 | 3930.06
| Aggregate Sub-base Course |  | 2 | each | 5670 | 11340 | 1.151% |  | 11340 | 11340 | 1.151% | COMPLETED |  | 100% | 497476.031 |  | 497476.03
Portland Cement Concrete Pavement, 230mm thk.
Reinforcing Steel (Line Drainage
T O T A L S | [5 empty] | 984959.89 | 100% | 0 | 984959.89 | 984959.89 | 100%
[5 empty] | % THIS ACCOMPLISHMENT |  |  |  | 100%
[5 empty] | TOTAL PROJECT COST |  |  |  | 984959.89
[5 empty] | TOTAL THIS ACCOMPLISHMENT |  |  |  | 984959.89
Less:
[5 empty] | TOTAL THIS VOUCHER |  |  |  | 984959.89
Requested by: |  | Prepared by: |  |  | Checked and Reviewed by: |  |  | Submitted by: |  |  | Approved:
|  | MA. VICTORIA E. REYES |  |  | ARNOLD L. MANUEL |  |  | VINCENT S. TAGUBA |  |  | MANUEL N. MAMBA, M.D.
Contractor |  | Engineer II |  |  | OIC- Chief of Construction Division |  |  | Asst. Provincial Engineer- Designate |  |  | Governor
Requested by: |  | Prepared by: |  |  | Checked by: |  |  |  | Submitted by: |  |  |  | Approved:
#REF! |  | MARISSA A. MACADANGDANG |  |  | MA. VICTORIA E. REYES |  |  |  | VINCENT S. TAGUBA |  |  |  | MANUEL N. MAMBA, M.D.
Contractor |  | Engineering Assistant |  |  | Engineer II |  |  |  | Asst. Provincial Engineer- Designate |  |  |  | Governor
STATEMENT OF WORK ACCOMPLISHMENT
As of _____________________, 2020
A. | CONCRETING OF FARM TO MARKET ROAD ZIMINILA
CAMALANIUGAN, CAGAYAN
ITEM | DESCRIPTION OF WORK |  | PROGRAMMED |  | UNIT | CONTRACT | WEIGHT | PROGRAMMED |  | UNIT | CONTRACT | ACCOMPLISHMENT |  |  | WEIGHT | REMARKS/
NO. |  |  | QUANTITY |  | PRICE | AMOUNT | % | QUANTITY |  | PRICE | AMOUNT | PREVIOUS | THIS PERIOD | TO DATE | % | STATUS
|  |  | ORIGINAL |  |  |  |  | VARIATION ORDER NO.1
105(1) | Sub Grade Preparation |  | 1075.8 | sq.m. | 102.17 | 109364.91 | 10.0228 | 1075.8 | Each | 102.17 | 109364.91 |  |  | 0 | 0% | on-going
200(1) | Aggregate Sub Base Coarse |  | 173.25 | sq.m. | 804.58 | 223636.89 | 20.4954 | 173.25 | Each | 1297.32 | 223636.89 |  |  | 0 | 0% | on-going
311(1)C | PCCP |  | 660 | sq.m. | 72.96 | 672973.03 | 61.6752 | 660 | cu.m. | 1024.78 | 672973.03 |  |  | 0 | 0% | on-going
B.9 | Mobilization/ Demobilization |  | 1 | l/s | 128.93 | 25951.88 | 2.3784 | 1 | cu.m. | 26082.29 | 25951.88 |  |  | 0 | 0% | on-going
B.5 | Billboards and Signages |  | 2 | each | 18.37 | 10196.76 | 0.93449 | 2 | sq.m. | 5124 | 10196.76 |  |  | 0 | 0% | on-going
B.7 | Occupational Health and Safety |  | 1 | l/s | 1208.89 | 28041.09 | 2.5698 | 1 | cu.m. | 28182 | 28041.09 |  |  | 0 | 0% | on-going
A.1.1(8a) | Provisions of Field Office for the Engineer |  | 1.83 | mos | 1291.19 | 20992.58 | 1.9239 | 1.83 | sq.m. | 11529 | 20992.58 |  |  | 0 | 0% | on-going
T O T A L S | [5 empty] | 1091157.14 | 100 |  |  |  | 1091157.14 | 0 | 0 | 0 | 0%
[5 empty] | % THIS ACCOMPLISHMENT | [6 empty] | 0 |  | % | [6 empty] | 16%
[5 empty] | TOTAL PROJECT COST | [6 empty] | 1091157.14 | [7 empty] | 109914.486 | 17586.3178 | 92328.1682
[5 empty] | TOTAL THIS ACCOMPLISHMENT | [6 empty] | 0 | [7 empty] | 139393.485 | 22302.9576 | 117090.5274
|  |  |  | Less: | MOBILIZATION | [12 empty] | 132 | 627 | 48153.6 | 7704.576 | 40449.024
[5 empty] | TOTAL THIS VOUCHER | [6 empty] | 0 | [5 empty] | 604.87 | 0.95 | 128.93 | 20.6288 | 108.3012
[18 empty] | 0.4 | 1.9 | 36.74 | 5.8784 | 30.8616
Requested by: |  | Prepared by: |  |  | Checked by: |  |  |  | Submitted by: |  |  |  | Approved: |  |  |  |  | 0.2 | 0.9 | 1208.89 | 193.4224 | 1015.4676
[18 empty] | 1067.5 |  | 2362.8777 | 378.0604 | 1984.8173
[20 empty] | 301199.0087 | 48191.8414 | 253007.1673
[18 empty] | #REF! |  | 1957.7936
EV INTERIOR CONSTRUCTION |  | MARISSA A. MACADANGDANG |  |  | MA. VICTORIA E. REYES |  |  |  | BASILIA B. FLORES |  |  |  | MANUEL N. MAMBA, M.D. | [6 empty] | 299241.2151
Contractor |  | Engineering Assistant |  |  | Engineer II |  |  |  | Provincial Engineer |  |  |  | Governor

## 500(1)a3 (2) (hidden)
NAME OF PROJECT: |  | Improvement of Road Network at Gattaran District Hospital
ITEM No.: |  | 500(1)a3 |  |  | UNIT: | ln.m.
DESCRIPTION: |  | Reiforced Concrete Pipe Culvert, 910mm Ø |  |  | QUANTITY: | 9
1. DIRECT COST | [10 empty] | Station Cover |  | Length (ln.m.)
1.a. | Materials | [8 empty] | 1 | 617.4305 | proposed | 7
Description |  |  | Unit | Quantity | Unit Cost | Amount |  |  |  | 2 | 758.7117 | R&R
RCPC, 610 mm. dia. |  |  | pcs. | 9 | 1200 | 10800 |  |  |  | 3 | 820.358 | R&R
Portland Cement |  |  | bags. | 6.966 | 260 | 1811.16 |  |  |  | 4 | 897.203 | R&R
Fine Aggregates |  |  | cu.m. | 0.396 | 555.28 | 219.89 |  |  |  | 5 | 935.6437 | R&R
Coarse Aggregates |  |  | cu.m. | 0.792 | 588.78 | 466.31 |  |  |  | 6 | 969.8518 | R&R
[5 empty] | 1.a. Total Material Cost = | 13297.36 |  |  |  | 7 | 1048.6413 | R&R
[10 empty] | 8 | 1286.1256 | R&R | 8
1.b. | Labor | [8 empty] | 9 | 1492.2047 | R&R | 8
Position |  |  | No. | Hours | Rate/hour | Amount |  |  |  | 10 | 1743.0888 | R&R
Foreman |  |  | 1 | 5 | 98.84 | 494.2 | 5 |  |  | 11 | 1917.0764 | R&R w/ prposed LD.
Mason |  |  | 1 | 5 | 81.09 | 405.45 | 5 |  |  | 12 | 1933.234 | R&R
Carpenter/Steelman |  |  | 1 | 5 | 81.09 | 405.45 | 5 |  |  | 13 | 2020.8597 | R&R
[5 empty] | Skilled Sub-Total | 1305.1 | 0 |  |  | 14 | 2169.4439 | R&R
Laborer |  |  | 4 | 5 | 62.38 | 1247.6 | 20 |  |  |  | Total |  | 70
[5 empty] | Unskilled Sub-Total | 1247.6 | 0 | [5 empty] | 16
[5 empty] | 1.b. Total Labor Cost = | 2552.7 | 35 | [5 empty] | 86
1.c. | Equipment Rental (Operated)
Make, Model & Capacity of Equipment |  |  | No. | Hours | Rate/hour | Amount |  | Manpower/ Equipment | No. | Quantities | ( Output/Hour ) | Duration
Backhoe, 0.80 cu.m.) |  |  | 1 | 2.5 | 1537 | 3842.5 |  |  | of Unit | l.m. |  | ( hours )
Plate Compactor (5Hp) |  |  | 1 | 2.5 | 123 | 307.5 |  | Backhoe | 1 |  |  | 2.5
Minor Tools (10% of Labor) |  |  |  |  | 255.27 | 255.27 |  | Plate Compactor | 1 |  |  | 2.5
[5 empty] | 1.c. Total Equipment Rental Cost = | 4405.27 |  | Foreman | 1 |  |  | 5
[8 empty] | Mason | 1 | 9 | 1.75 | 5
[5 empty] | 1. Total Direct Cost (1a+1b+1c) = | 20255.33 |  | Carpenter/Steelman | 1 |  |  | 5
2. INDIRECT COST | [7 empty] | Laborer | 4 |  |  | 5
Description |  |  |  |  | % | Amount |  |  |  |  | No. of Days = | 0.625
2.a. | Overhead, Contingencies, and Misc. Expenses (OCM) |  |  |  | 10% | 2025.53
2.b. | Contractor's Profit (CP) |  |  |  | 8% | 1620.43
2.c. | Contractor's Tax (CT) |  |  |  | 5% | 1195.06
[5 empty] | 2. Total Indirect Cost (2a+2b+2c) = | 4841.02
A. | Total Item Cost (1+2) |  |  |  |  | 25096.35
B. | Total Quantity of Item of Work |  |  |  |  | 9
C. | Unit |  |  |  |  | ln.m.
D. | Item Unit Cost (A / B) |  |  |  |  | 2788.48
|  |  |  | Adjusted Item Cost |  | 25096.32